## Executive Summary
Metric | Value
Report Generated | 23/7/2026, 9:11:59 am
Project | ERP/CRM Full Project
Source | Local repo docs, route/model/page scan, and git status
Overall completion from roadmap | 52.9% complete / 47.1% remaining
Detailed feature rows in this workbook | 127
Average completion from detailed rows | 63.5%
Complete | 61
Partial | 20
Needs Verification | 15
Pending | 1
Not Started | 30
Main strength | CRM core flow and RBAC/auth foundation are strong.
Main risk | Several newly added ERP/Auth features need database/API/frontend verification before calling them complete.

## All Feature Details
Area | Module | Feature | Status | Completion % | Priority | Phase | Details / Evidence
ERP | Master Data | Item/Product Master | Complete | 100 | High | Phase 1 | Products backend/frontend CRUD exists.
ERP | Master Data | Product Category/Sub-category | Complete | 100 | High | Phase 1 | ProductCategories module exists.
ERP | Master Data | Units/UOM | Complete | 100 | High | Phase 1 | Units module exists; conversion depth still needs business validation.
ERP | Master Data | Warehouse/Location Master | Complete | 100 | High | Phase 1 | Warehouses module exists.
ERP | Master Data | Supplier/Vendor Master | Complete | 100 | High | Phase 1 | Suppliers module exists.
ERP | Master Data | Customer Master | Complete | 100 | High | Phase 1 | Customers module exists.
ERP | Master Data | Brand Master | Complete | 100 | Medium | Phase 1 | Brands module exists.
ERP | Master Data | Tax Configuration | Complete | 100 | High | Phase 1 | Taxes and ProductTaxMap modules exist.
ERP | Master Data | Batch/Serial Attributes | Complete | 100 | High | Phase 1 | BatchSerial tracking exists.
ERP | Master Data | Bin/Rack Master | Partial | 50 | Medium | Phase 2 | Basic warehouse locations exist; dedicated bin/rack workflow not confirmed.
ERP | Master Data | Barcode Setup/Printing | Partial | 40 | Low | Phase 3 | Barcode field/helpers exist; complete printing/scanning workflow not confirmed.
ERP | Master Data | HSN/SAC Code Master | Needs Verification | 70 | Medium | Phase 2 | New HSN model/controller/route exists; needs API/UI testing.
ERP | Master Data | Price List Master | Needs Verification | 70 | Medium | Phase 2 | New price list model/controller/route exists; needs API/UI testing.
ERP | Master Data | Size/Color Attributes | Not Started | 0 | Low | Phase 3 | No dedicated item variant attribute module found.
ERP | Purchase | Purchase Requisition | Complete | 100 | High | Phase 1 | PurchaseRequisitions module exists.
ERP | Purchase | Purchase Order | Complete | 100 | High | Phase 1 | PurchaseOrders with items exists.
ERP | Purchase | Goods Receipt Note | Complete | 100 | High | Phase 1 | GRN module exists.
ERP | Purchase | Purchase Return/Debit Note | Complete | 100 | High | Phase 1 | PurchaseReturns module exists.
ERP | Purchase | PO Approval Workflow | Partial | 60 | High | Phase 1 | Generic approval system exists; PO-specific flow not fully confirmed.
ERP | Purchase | Purchase Order Tracking | Partial | 50 | Medium | Phase 2 | Basic status tracking exists; advanced tracking not confirmed.
ERP | Purchase | Request for Quotation | Needs Verification | 70 | Medium | Phase 2 | New RFQ model/controller/route exists; needs full testing.
ERP | Purchase | PO-GRN-Invoice Matching | Needs Verification | 70 | High | Phase 2 | New invoice match model/controller/route exists; needs full testing.
ERP | Purchase | Blanket/Contract Orders | Not Started | 0 | Low | Phase 3 | No dedicated module found.
ERP | Sales | Sales Quotation | Complete | 100 | High | Phase 1 | SalesQuotations module exists.
ERP | Sales | Sales Order | Complete | 100 | High | Phase 1 | SalesOrders module exists.
ERP | Sales | Delivery Challan/Dispatch | Complete | 100 | High | Phase 1 | DeliveryChallans module exists.
ERP | Sales | Sales Return/Credit Note | Complete | 100 | High | Phase 1 | SalesReturns module exists.
ERP | Sales | Invoice Generation | Complete | 100 | High | Phase 1 | CRM invoices module exists.
ERP | Sales | Sales Order Approval | Partial | 60 | High | Phase 1 | Generic approval system exists; SO-specific flow not fully confirmed.
ERP | Sales | Backorder Management | Partial | 40 | Medium | Phase 2 | Basic handling may exist; dedicated tracking/reporting not found.
ERP | Inventory | Stock Inward Entry | Complete | 100 | High | Phase 1 | Covered through GRN process.
ERP | Inventory | Stock Outward Entry | Complete | 100 | High | Phase 1 | Covered through delivery challan/sales flow.
ERP | Inventory | Stock Transfer | Complete | 100 | High | Phase 1 | StockTransfers module exists.
ERP | Inventory | Stock Adjustment | Complete | 100 | High | Phase 1 | StockAdjustments module exists.
ERP | Inventory | Stock Movements/Ledger | Complete | 100 | High | Phase 1 | StockMovements module exists.
ERP | Inventory | Stock Reservation/Allocation | Partial | 30 | Medium | Phase 2 | Dedicated reservation module not found.
ERP | Inventory | Expiry Date Management | Not Started | 0 | Medium | Phase 2 | No complete expiry tracking workflow found.
ERP | Inventory | Stock Aging Report | Not Started | 0 | Medium | Phase 2 | No dedicated aging report found.
ERP | Inventory | Reorder Levels | Needs Verification | 70 | High | Phase 1 | New reorder model/controller/route and frontend page exist; needs end-to-end testing.
ERP | Inventory | Auto Replenishment | Needs Verification | 50 | High | Phase 1 | Reorder foundation exists; automatic PO/replenishment behavior needs validation.
ERP | Inventory | Min-Max Stock Settings | Needs Verification | 60 | High | Phase 1 | Likely part of new ReorderLevels; needs validation.
ERP | WMS | Warehouse Transfer Note | Complete | 100 | High | Phase 1 | Covered by StockTransfers.
ERP | WMS | Bin/Location Mapping | Partial | 50 | Medium | Phase 2 | Basic warehouse locations only.
ERP | WMS | Packing & Shipment | Partial | 40 | Medium | Phase 2 | Basic delivery challan workflow only.
ERP | WMS | Putaway Management | Not Started | 0 | Medium | Phase 3 | No dedicated workflow found.
ERP | WMS | Picking List Generation | Not Started | 0 | Medium | Phase 3 | No dedicated workflow found.
ERP | WMS | Cycle Count | Not Started | 0 | Low | Phase 3 | No dedicated workflow found.
ERP | WMS | Physical Stock Verification | Not Started | 0 | Low | Phase 3 | No dedicated workflow found.
ERP | WMS | Cross-Docking | Not Started | 0 | Low | Phase 4 | No dedicated workflow found.
ERP | Costing | Costing Method Setup | Needs Verification | 70 | High | Phase 1 | New costing method model and stock valuation files exist; needs testing.
ERP | Costing | Stock Valuation Report | Needs Verification | 70 | High | Phase 1 | New stock valuation route/controller/frontend page exists; needs testing.
ERP | Costing | Landed Cost Allocation | Needs Verification | 55 | Medium | Phase 2 | New landed cost model exists; route/UI completeness needs validation.
ERP | Costing | Cost Adjustment Entries | Needs Verification | 55 | Medium | Phase 2 | New cost adjustment model exists; route/UI completeness needs validation.
ERP | Quality Control | Quality Inspection Setup | Partial | 30 | Medium | Phase 2 | QualityControl model exists but integration is incomplete.
ERP | Quality Control | QC on GRN | Not Started | 0 | Medium | Phase 2 | No full GRN QC workflow confirmed.
ERP | Quality Control | Rejected/Quarantine Stock | Not Started | 0 | Medium | Phase 2 | No quarantine workflow confirmed.
ERP | Quality Control | QC Certificates | Not Started | 0 | Low | Phase 3 | No certificate workflow confirmed.
ERP | Production | Bill of Materials | Complete | 100 | High | Phase 1 | BOM module exists.
ERP | Production | Work Order/Job Card | Complete | 100 | High | Phase 1 | ProductionOrders module exists.
ERP | Production | Material Requisition | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Production | Raw Material Issue | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Production | Finished Goods Receipt | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Production | By-product/Scrap Entry | Not Started | 0 | Low | Phase 3 | No dedicated module found.
ERP | Reports | Stock Movement Report | Complete | 100 | High | Phase 1 | StockMovements module exists.
ERP | Reports | Batch/Serial Traceability | Complete | 100 | High | Phase 1 | BatchSerial module exists.
ERP | Reports | Profit/Loss Reports | Complete | 100 | High | Phase 1 | ProfitLossReports module exists.
ERP | Reports | Stock Summary | Partial | 50 | Medium | Phase 2 | Basic stock reporting exists.
ERP | Reports | Item-wise Sales/Purchase Analysis | Partial | 60 | Medium | Phase 2 | Basic reporting exists; advanced analytics not confirmed.
ERP | Reports | ABC Analysis | Not Started | 0 | Medium | Phase 3 | No dedicated analytics found.
ERP | Reports | Slow/Non-moving Stock | Not Started | 0 | Medium | Phase 3 | No dedicated report found.
ERP | Reports | Vendor Performance | Not Started | 0 | Medium | Phase 3 | No dedicated report found.
ERP | Reports | GRN vs PO Reconciliation | Not Started | 0 | Medium | Phase 2 | No dedicated reconciliation report confirmed.
ERP | Utilities | Import/Export Excel/CSV | Complete | 100 | High | Phase 1 | DataImportExport module exists.
ERP | Utilities | Approval Workflow Configuration | Complete | 100 | High | Phase 1 | Approval workflow tables exist.
ERP | Utilities | Audit Trail/Logs | Complete | 100 | High | Phase 1 | AuditLogs and security tracking exist.
ERP | Utilities | Multi-Currency | Not Started | 0 | Medium | Phase 2 | No multi-currency support found.
ERP | Utilities | Financial Year/Periods | Needs Verification | 70 | Medium | Phase 2 | New financial year model/controller/route exists; needs testing.
CRM | Core CRM | Leads Management | Complete | 100 | High | Phase 1 | Full lead entity with source, status, rating, assignment, conversion fields.
CRM | Core CRM | Opportunities Management | Complete | 100 | High | Phase 1 | Opportunity budget, stage, probability, close handling exists.
CRM | Core CRM | Accounts Management | Complete | 100 | High | Phase 1 | Account CRUD and ownership fields exist.
CRM | Core CRM | Contacts Management | Complete | 100 | High | Phase 1 | Contact details and account association exist.
CRM | Core CRM | Activities Management | Complete | 100 | High | Phase 1 | Activities with type, due dates, status, priority, reminders.
CRM | Core CRM | Cases/Support Tickets | Complete | 100 | High | Phase 1 | Cases with status, priority, assignment, resolution.
CRM | Core CRM | Quotes Management | Complete | 100 | High | Phase 1 | Quote numbering, totals, status, terms.
CRM | Core CRM | Invoices Management | Complete | 100 | High | Phase 1 | Invoice numbering, payment status, due date, totals.
CRM | Core CRM | Payments Management | Complete | 100 | High | Phase 1 | Payment recording, methods, references, invoice association.
CRM | Core CRM | Retentions/Follow-ups | Complete | 100 | Medium | Phase 1 | Retention type, status, next action, reminders.
CRM | Core CRM | Presales Management | Partial | 70 | Medium | Phase 2 | Model and page exist; integration/details need verification.
CRM | Master Data | Lead Sources | Complete | 100 | High | Phase 1 | Master data exists.
CRM | Master Data | Industries | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Master Data | Sales Stages | Complete | 100 | High | Phase 1 | Master data exists.
CRM | Master Data | Follow-up Types | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Master Data | Task Types | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Master Data | Payment Terms | Not Started | 0 | Medium | Phase 2 | No dedicated master found.
CRM | Master Data | Case Categories/Resolution Codes | Not Started | 0 | Low | Phase 3 | No dedicated master found.
CRM | Workflow | Lead to Opportunity | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Opportunity to Quote | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Quote to Invoice | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Invoice to Payment | Complete | 100 | High | Phase 1 | Payment tracking exists.
CRM | Workflow | Automations and Reminders | Partial | 60 | Medium | Phase 2 | CRM jobs and automation services exist; coverage needs validation.
CRM | Workflow | Visual Workflow Builder | Not Started | 0 | Medium | Phase 3 | No builder found.
CRM | Workflow | SLA Management | Partial | 40 | Medium | Phase 3 | Case SLA job exists; full configuration flow not confirmed.
CRM | Analytics | Sales Pipeline Dashboard | Complete | 100 | High | Phase 1 | CRM dashboard/components exist.
CRM | Analytics | Lead/Opportunity Reports | Complete | 100 | High | Phase 1 | Basic reporting exists.
CRM | Analytics | Conversion Analytics | Not Started | 0 | Medium | Phase 2 | Dedicated analytics not confirmed.
CRM | Analytics | Sales Forecasting | Not Started | 0 | Medium | Phase 2 | No dedicated forecasting module found.
CRM | Analytics | Custom Report Builder | Not Started | 0 | Low | Phase 3 | No builder found.
CRM | Integration | Email Sending/Templates/Tracking | Pending | 20 | High | Phase 2 | Nodemailer exists; full CRM email integration not confirmed.
CRM | Integration | Calendar Sync | Not Started | 0 | Medium | Phase 2 | No calendar integration found.
CRM | Integration | Document Management | Needs Verification | 70 | Medium | Phase 2 | New document model/controller/route exists; needs CRM entity integration testing.
CRM | Integration | Customer Portal | Partial | 40 | Low | Phase 3 | UserPortal components exist; customer portal completeness not confirmed.
CRM | Integration | SMS/Social/Call Recording | Not Started | 0 | Low | Phase 4 | No integrations found.
User/RBAC | Authentication | JWT Login/Logout/Refresh | Complete | 100 | High | Phase 1 | Auth service, refresh tokens, session management exist.
User/RBAC | Authentication | Password Reset/Email Verification | Complete | 100 | High | Phase 1 | Services and routes documented as complete.
User/RBAC | Authentication | 2FA/TOTP | Needs Verification | 70 | High | Phase 1 | New User2FA model/controller/routes exist; needs login-flow testing.
User/RBAC | Authentication | OAuth | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | Authentication | LDAP/Active Directory | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | Security | Login History/Suspicious Detection | Complete | 100 | High | Phase 1 | LoginHistory and security services exist.
User/RBAC | Security | IP Whitelisting | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | RBAC | Roles and Permissions | Complete | 100 | High | Phase 1 | Database-driven RBAC with modules/permissions/menus.
User/RBAC | RBAC | Menu Permissions | Complete | 100 | High | Phase 1 | Menu visibility control exists.
User/RBAC | RBAC | Company Isolation | Complete | 100 | High | Phase 1 | Company scope middleware/utilities exist.
User/RBAC | RBAC | User Type Management UI | Needs Verification | 70 | High | Phase 1 | New frontend UserTypes page exists; needs testing.
User/RBAC | Users | User Registration/Profile/List | Complete | 100 | High | Phase 1 | Frontend and backend pages/controllers exist.
User/RBAC | Users | Organization Chart | Complete | 100 | Medium | Phase 1 | Classic org chart component exists.
User/RBAC | Users | Bulk User Import | Partial | 40 | Medium | Phase 2 | Import utilities exist; user-specific flow not confirmed.
User/RBAC | Users | User Impersonation | Not Started | 0 | Medium | Phase 3 | No implementation found.

## Completed
Area | Module | Feature | Status | Completion % | Priority | Phase | Details / Evidence
ERP | Master Data | Item/Product Master | Complete | 100 | High | Phase 1 | Products backend/frontend CRUD exists.
ERP | Master Data | Product Category/Sub-category | Complete | 100 | High | Phase 1 | ProductCategories module exists.
ERP | Master Data | Units/UOM | Complete | 100 | High | Phase 1 | Units module exists; conversion depth still needs business validation.
ERP | Master Data | Warehouse/Location Master | Complete | 100 | High | Phase 1 | Warehouses module exists.
ERP | Master Data | Supplier/Vendor Master | Complete | 100 | High | Phase 1 | Suppliers module exists.
ERP | Master Data | Customer Master | Complete | 100 | High | Phase 1 | Customers module exists.
ERP | Master Data | Brand Master | Complete | 100 | Medium | Phase 1 | Brands module exists.
ERP | Master Data | Tax Configuration | Complete | 100 | High | Phase 1 | Taxes and ProductTaxMap modules exist.
ERP | Master Data | Batch/Serial Attributes | Complete | 100 | High | Phase 1 | BatchSerial tracking exists.
ERP | Purchase | Purchase Requisition | Complete | 100 | High | Phase 1 | PurchaseRequisitions module exists.
ERP | Purchase | Purchase Order | Complete | 100 | High | Phase 1 | PurchaseOrders with items exists.
ERP | Purchase | Goods Receipt Note | Complete | 100 | High | Phase 1 | GRN module exists.
ERP | Purchase | Purchase Return/Debit Note | Complete | 100 | High | Phase 1 | PurchaseReturns module exists.
ERP | Sales | Sales Quotation | Complete | 100 | High | Phase 1 | SalesQuotations module exists.
ERP | Sales | Sales Order | Complete | 100 | High | Phase 1 | SalesOrders module exists.
ERP | Sales | Delivery Challan/Dispatch | Complete | 100 | High | Phase 1 | DeliveryChallans module exists.
ERP | Sales | Sales Return/Credit Note | Complete | 100 | High | Phase 1 | SalesReturns module exists.
ERP | Sales | Invoice Generation | Complete | 100 | High | Phase 1 | CRM invoices module exists.
ERP | Inventory | Stock Inward Entry | Complete | 100 | High | Phase 1 | Covered through GRN process.
ERP | Inventory | Stock Outward Entry | Complete | 100 | High | Phase 1 | Covered through delivery challan/sales flow.
ERP | Inventory | Stock Transfer | Complete | 100 | High | Phase 1 | StockTransfers module exists.
ERP | Inventory | Stock Adjustment | Complete | 100 | High | Phase 1 | StockAdjustments module exists.
ERP | Inventory | Stock Movements/Ledger | Complete | 100 | High | Phase 1 | StockMovements module exists.
ERP | WMS | Warehouse Transfer Note | Complete | 100 | High | Phase 1 | Covered by StockTransfers.
ERP | Production | Bill of Materials | Complete | 100 | High | Phase 1 | BOM module exists.
ERP | Production | Work Order/Job Card | Complete | 100 | High | Phase 1 | ProductionOrders module exists.
ERP | Reports | Stock Movement Report | Complete | 100 | High | Phase 1 | StockMovements module exists.
ERP | Reports | Batch/Serial Traceability | Complete | 100 | High | Phase 1 | BatchSerial module exists.
ERP | Reports | Profit/Loss Reports | Complete | 100 | High | Phase 1 | ProfitLossReports module exists.
ERP | Utilities | Import/Export Excel/CSV | Complete | 100 | High | Phase 1 | DataImportExport module exists.
ERP | Utilities | Approval Workflow Configuration | Complete | 100 | High | Phase 1 | Approval workflow tables exist.
ERP | Utilities | Audit Trail/Logs | Complete | 100 | High | Phase 1 | AuditLogs and security tracking exist.
CRM | Core CRM | Leads Management | Complete | 100 | High | Phase 1 | Full lead entity with source, status, rating, assignment, conversion fields.
CRM | Core CRM | Opportunities Management | Complete | 100 | High | Phase 1 | Opportunity budget, stage, probability, close handling exists.
CRM | Core CRM | Accounts Management | Complete | 100 | High | Phase 1 | Account CRUD and ownership fields exist.
CRM | Core CRM | Contacts Management | Complete | 100 | High | Phase 1 | Contact details and account association exist.
CRM | Core CRM | Activities Management | Complete | 100 | High | Phase 1 | Activities with type, due dates, status, priority, reminders.
CRM | Core CRM | Cases/Support Tickets | Complete | 100 | High | Phase 1 | Cases with status, priority, assignment, resolution.
CRM | Core CRM | Quotes Management | Complete | 100 | High | Phase 1 | Quote numbering, totals, status, terms.
CRM | Core CRM | Invoices Management | Complete | 100 | High | Phase 1 | Invoice numbering, payment status, due date, totals.
CRM | Core CRM | Payments Management | Complete | 100 | High | Phase 1 | Payment recording, methods, references, invoice association.
CRM | Core CRM | Retentions/Follow-ups | Complete | 100 | Medium | Phase 1 | Retention type, status, next action, reminders.
CRM | Master Data | Lead Sources | Complete | 100 | High | Phase 1 | Master data exists.
CRM | Master Data | Industries | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Master Data | Sales Stages | Complete | 100 | High | Phase 1 | Master data exists.
CRM | Master Data | Follow-up Types | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Master Data | Task Types | Complete | 100 | Medium | Phase 1 | Master data exists.
CRM | Workflow | Lead to Opportunity | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Opportunity to Quote | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Quote to Invoice | Complete | 100 | High | Phase 1 | Conversion workflow exists.
CRM | Workflow | Invoice to Payment | Complete | 100 | High | Phase 1 | Payment tracking exists.
CRM | Analytics | Sales Pipeline Dashboard | Complete | 100 | High | Phase 1 | CRM dashboard/components exist.
CRM | Analytics | Lead/Opportunity Reports | Complete | 100 | High | Phase 1 | Basic reporting exists.
User/RBAC | Authentication | JWT Login/Logout/Refresh | Complete | 100 | High | Phase 1 | Auth service, refresh tokens, session management exist.
User/RBAC | Authentication | Password Reset/Email Verification | Complete | 100 | High | Phase 1 | Services and routes documented as complete.
User/RBAC | Security | Login History/Suspicious Detection | Complete | 100 | High | Phase 1 | LoginHistory and security services exist.
User/RBAC | RBAC | Roles and Permissions | Complete | 100 | High | Phase 1 | Database-driven RBAC with modules/permissions/menus.
User/RBAC | RBAC | Menu Permissions | Complete | 100 | High | Phase 1 | Menu visibility control exists.
User/RBAC | RBAC | Company Isolation | Complete | 100 | High | Phase 1 | Company scope middleware/utilities exist.
User/RBAC | Users | User Registration/Profile/List | Complete | 100 | High | Phase 1 | Frontend and backend pages/controllers exist.
User/RBAC | Users | Organization Chart | Complete | 100 | Medium | Phase 1 | Classic org chart component exists.

## Pending Partial
Area | Module | Feature | Status | Completion % | Priority | Phase | Details / Evidence
ERP | Master Data | Bin/Rack Master | Partial | 50 | Medium | Phase 2 | Basic warehouse locations exist; dedicated bin/rack workflow not confirmed.
ERP | Master Data | Barcode Setup/Printing | Partial | 40 | Low | Phase 3 | Barcode field/helpers exist; complete printing/scanning workflow not confirmed.
ERP | Purchase | PO Approval Workflow | Partial | 60 | High | Phase 1 | Generic approval system exists; PO-specific flow not fully confirmed.
ERP | Purchase | Purchase Order Tracking | Partial | 50 | Medium | Phase 2 | Basic status tracking exists; advanced tracking not confirmed.
ERP | Sales | Sales Order Approval | Partial | 60 | High | Phase 1 | Generic approval system exists; SO-specific flow not fully confirmed.
ERP | Sales | Backorder Management | Partial | 40 | Medium | Phase 2 | Basic handling may exist; dedicated tracking/reporting not found.
ERP | Inventory | Stock Reservation/Allocation | Partial | 30 | Medium | Phase 2 | Dedicated reservation module not found.
ERP | WMS | Bin/Location Mapping | Partial | 50 | Medium | Phase 2 | Basic warehouse locations only.
ERP | WMS | Packing & Shipment | Partial | 40 | Medium | Phase 2 | Basic delivery challan workflow only.
ERP | Quality Control | Quality Inspection Setup | Partial | 30 | Medium | Phase 2 | QualityControl model exists but integration is incomplete.
ERP | Production | Material Requisition | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Production | Raw Material Issue | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Production | Finished Goods Receipt | Partial | 50 | Medium | Phase 2 | May be part of production module; workflow needs validation.
ERP | Reports | Stock Summary | Partial | 50 | Medium | Phase 2 | Basic stock reporting exists.
ERP | Reports | Item-wise Sales/Purchase Analysis | Partial | 60 | Medium | Phase 2 | Basic reporting exists; advanced analytics not confirmed.
CRM | Core CRM | Presales Management | Partial | 70 | Medium | Phase 2 | Model and page exist; integration/details need verification.
CRM | Workflow | Automations and Reminders | Partial | 60 | Medium | Phase 2 | CRM jobs and automation services exist; coverage needs validation.
CRM | Workflow | SLA Management | Partial | 40 | Medium | Phase 3 | Case SLA job exists; full configuration flow not confirmed.
CRM | Integration | Email Sending/Templates/Tracking | Pending | 20 | High | Phase 2 | Nodemailer exists; full CRM email integration not confirmed.
CRM | Integration | Customer Portal | Partial | 40 | Low | Phase 3 | UserPortal components exist; customer portal completeness not confirmed.
User/RBAC | Users | Bulk User Import | Partial | 40 | Medium | Phase 2 | Import utilities exist; user-specific flow not confirmed.

## Not Started
Area | Module | Feature | Status | Completion % | Priority | Phase | Details / Evidence
ERP | Master Data | Size/Color Attributes | Not Started | 0 | Low | Phase 3 | No dedicated item variant attribute module found.
ERP | Purchase | Blanket/Contract Orders | Not Started | 0 | Low | Phase 3 | No dedicated module found.
ERP | Inventory | Expiry Date Management | Not Started | 0 | Medium | Phase 2 | No complete expiry tracking workflow found.
ERP | Inventory | Stock Aging Report | Not Started | 0 | Medium | Phase 2 | No dedicated aging report found.
ERP | WMS | Putaway Management | Not Started | 0 | Medium | Phase 3 | No dedicated workflow found.
ERP | WMS | Picking List Generation | Not Started | 0 | Medium | Phase 3 | No dedicated workflow found.
ERP | WMS | Cycle Count | Not Started | 0 | Low | Phase 3 | No dedicated workflow found.
ERP | WMS | Physical Stock Verification | Not Started | 0 | Low | Phase 3 | No dedicated workflow found.
ERP | WMS | Cross-Docking | Not Started | 0 | Low | Phase 4 | No dedicated workflow found.
ERP | Quality Control | QC on GRN | Not Started | 0 | Medium | Phase 2 | No full GRN QC workflow confirmed.
ERP | Quality Control | Rejected/Quarantine Stock | Not Started | 0 | Medium | Phase 2 | No quarantine workflow confirmed.
ERP | Quality Control | QC Certificates | Not Started | 0 | Low | Phase 3 | No certificate workflow confirmed.
ERP | Production | By-product/Scrap Entry | Not Started | 0 | Low | Phase 3 | No dedicated module found.
ERP | Reports | ABC Analysis | Not Started | 0 | Medium | Phase 3 | No dedicated analytics found.
ERP | Reports | Slow/Non-moving Stock | Not Started | 0 | Medium | Phase 3 | No dedicated report found.
ERP | Reports | Vendor Performance | Not Started | 0 | Medium | Phase 3 | No dedicated report found.
ERP | Reports | GRN vs PO Reconciliation | Not Started | 0 | Medium | Phase 2 | No dedicated reconciliation report confirmed.
ERP | Utilities | Multi-Currency | Not Started | 0 | Medium | Phase 2 | No multi-currency support found.
CRM | Master Data | Payment Terms | Not Started | 0 | Medium | Phase 2 | No dedicated master found.
CRM | Master Data | Case Categories/Resolution Codes | Not Started | 0 | Low | Phase 3 | No dedicated master found.
CRM | Workflow | Visual Workflow Builder | Not Started | 0 | Medium | Phase 3 | No builder found.
CRM | Analytics | Conversion Analytics | Not Started | 0 | Medium | Phase 2 | Dedicated analytics not confirmed.
CRM | Analytics | Sales Forecasting | Not Started | 0 | Medium | Phase 2 | No dedicated forecasting module found.
CRM | Analytics | Custom Report Builder | Not Started | 0 | Low | Phase 3 | No builder found.
CRM | Integration | Calendar Sync | Not Started | 0 | Medium | Phase 2 | No calendar integration found.
CRM | Integration | SMS/Social/Call Recording | Not Started | 0 | Low | Phase 4 | No integrations found.
User/RBAC | Authentication | OAuth | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | Authentication | LDAP/Active Directory | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | Security | IP Whitelisting | Not Started | 0 | Medium | Phase 3 | Explicitly listed as not implemented.
User/RBAC | Users | User Impersonation | Not Started | 0 | Medium | Phase 3 | No implementation found.

## Needs Verification
Area | Module | Feature | Status | Completion % | Priority | Phase | Details / Evidence
ERP | Master Data | HSN/SAC Code Master | Needs Verification | 70 | Medium | Phase 2 | New HSN model/controller/route exists; needs API/UI testing.
ERP | Master Data | Price List Master | Needs Verification | 70 | Medium | Phase 2 | New price list model/controller/route exists; needs API/UI testing.
ERP | Purchase | Request for Quotation | Needs Verification | 70 | Medium | Phase 2 | New RFQ model/controller/route exists; needs full testing.
ERP | Purchase | PO-GRN-Invoice Matching | Needs Verification | 70 | High | Phase 2 | New invoice match model/controller/route exists; needs full testing.
ERP | Inventory | Reorder Levels | Needs Verification | 70 | High | Phase 1 | New reorder model/controller/route and frontend page exist; needs end-to-end testing.
ERP | Inventory | Auto Replenishment | Needs Verification | 50 | High | Phase 1 | Reorder foundation exists; automatic PO/replenishment behavior needs validation.
ERP | Inventory | Min-Max Stock Settings | Needs Verification | 60 | High | Phase 1 | Likely part of new ReorderLevels; needs validation.
ERP | Costing | Costing Method Setup | Needs Verification | 70 | High | Phase 1 | New costing method model and stock valuation files exist; needs testing.
ERP | Costing | Stock Valuation Report | Needs Verification | 70 | High | Phase 1 | New stock valuation route/controller/frontend page exists; needs testing.
ERP | Costing | Landed Cost Allocation | Needs Verification | 55 | Medium | Phase 2 | New landed cost model exists; route/UI completeness needs validation.
ERP | Costing | Cost Adjustment Entries | Needs Verification | 55 | Medium | Phase 2 | New cost adjustment model exists; route/UI completeness needs validation.
ERP | Utilities | Financial Year/Periods | Needs Verification | 70 | Medium | Phase 2 | New financial year model/controller/route exists; needs testing.
CRM | Integration | Document Management | Needs Verification | 70 | Medium | Phase 2 | New document model/controller/route exists; needs CRM entity integration testing.
User/RBAC | Authentication | 2FA/TOTP | Needs Verification | 70 | High | Phase 1 | New User2FA model/controller/routes exist; needs login-flow testing.
User/RBAC | RBAC | User Type Management UI | Needs Verification | 70 | High | Phase 1 | New frontend UserTypes page exists; needs testing.

## New Files To Verify
Area | Feature | Files / Evidence | Current Finding | Next Validation Step
Inventory | Stock Valuation | ERPCRMServer/Models/InventoryManagement/StockValuation.js; routes/Inventory/stockValuation | Backend and frontend page appear newly added. | Run API smoke test and confirm valuation formulas.
Inventory | Costing Method | ERPCRMServer/Models/InventoryManagement/CostingMethod.js | Model exists. | Confirm controller coverage and DB table creation.
Inventory | Landed Cost | ERPCRMServer/Models/InventoryManagement/LandedCost.js | Model exists. | Confirm route/controller/UI coverage.
Inventory | Cost Adjustment | ERPCRMServer/Models/InventoryManagement/CostAdjustment.js | Model exists. | Confirm route/controller/UI coverage.
Inventory | Reorder Levels | ERPCRMServer/controllers/InventoryApis/reorderLevelController.js; clientui/src/features/inventory/pages/ReorderLevelsPage.jsx | Backend route and frontend page exist. | Test create/update alerts and auto replenish.
Inventory | RFQ | ERPCRMServer/controllers/InventoryApis/rfqController.js; routes/Inventory/rfq | Backend files exist. | Test RFQ lifecycle and supplier linking.
Inventory | Invoice Matching | ERPCRMServer/controllers/InventoryApis/invoiceMatchController.js; routes/Inventory/invoiceMatch | Backend files exist. | Test PO-GRN-Invoice 3-way matching.
Inventory | HSN Code | ERPCRMServer/controllers/InventoryApis/hsnCodeController.js; routes/Inventory/hsnCode | Backend files exist. | Test CRUD and product/tax integration.
Inventory | Price List | ERPCRMServer/controllers/InventoryApis/priceListController.js; routes/Inventory/priceList | Backend files exist. | Test pricing rules and frontend access.
Inventory | Financial Year | ERPCRMServer/controllers/InventoryApis/financialYearController.js; routes/Inventory/financialYear | Backend files exist. | Test active year, period close, accounting rules.
CRM/System | Documents | ERPCRMServer/controllers/InventoryApis/documentController.js; routes/Inventory/documents | Document management backend exists. | Confirm CRM entity attachments/versioning/share flow.
Auth | Two Factor Authentication | ERPCRMServer/controllers/auth/twoFactorController.js; routes/Auth/twoFactorRoutes.js | 2FA backend files exist. | Test setup, verify, disable, backup codes, login enforcement.
Database | Schema Conflict Fix | ERPCRMServer/docs/SCHEMA_FIX_REPORT.md; scripts/fix_database_schema.js | Fix documented for ModuleId/PermissionId conflicts. | Run verify_schema.js against target DB.

## Roadmap
Phase | Focus | Timeline | Major Work | Target
Phase 1 | Critical Core | Months 1-4 | Stock valuation, reorder levels, 2FA, documents, audit improvements | Raise overall completion to about 75%
Phase 2 | Process Enhancement | Months 5-8 | QC, financial settings, RFQ/invoice matching, reports | Raise overall completion to about 85%
Phase 3 | Advanced Features | Months 9-12 | WMS, analytics, enterprise user/security features | Raise overall completion to about 95%
Phase 4 | Integrations & Polish | Months 13-16 | E-commerce, logistics, calendar/SMS/social integrations, final hardening | Reach 100%

## Timeline 12 Weeks
Phase | Focus | Start Date | End Date | Planned Work | Exit Criteria
Phase 1 | Frontend completion and verification | 2026-07-23 | 2026-08-05 | Verify and finish Financial Year, Documents, RFQ, Price Lists, HSN/SAC, Invoice Matching, reports, 2FA UI, reorder alerts. | New backend-backed pages are usable and verified end to end.
Phase 2 | Core backend hardening | 2026-08-06 | 2026-08-19 | WMS controllers, validation across controllers, stock reservation, enhanced audit logging, email templates. | Core ERP APIs are stable, validated, and ready for workflow testing.
Phase 3 | Security and RBAC | 2026-08-20 | 2026-09-02 | Field-level permissions, record-level permissions, hierarchy access, department scoping, branch scoping. | Role and hierarchy access rules match business expectations.
Phase 4 | Advanced ERP features | 2026-09-03 | 2026-09-16 | Customer portal, multi-currency verification, marketing automation, workflow automation, physical inventory. | Advanced operating workflows are functionally complete.
Phase 5 | Integrations | 2026-09-17 | 2026-09-30 | E-commerce sync, shipping integration, SMS notifications, calendar sync, social media integration. | External integrations are connected or ready behind provider credentials.
Phase 6 | Testing and polish | 2026-10-01 | 2026-10-14 | Unit tests, integration tests, performance testing, security testing, bug fixes, documentation. | Release candidate ready for UAT/deployment decision.

## Git Pending Changes
Change Type | Path
Deleted | ERPCRMServer/.git_disabled/HEAD
Deleted | ERPCRMServer/.git_disabled/config
Deleted | ERPCRMServer/.git_disabled/description
Deleted | ERPCRMServer/.git_disabled/hooks/applypatch-msg.sample
Deleted | ERPCRMServer/.git_disabled/hooks/commit-msg.sample
Deleted | ERPCRMServer/.git_disabled/hooks/fsmonitor-watchman.sample
Deleted | ERPCRMServer/.git_disabled/hooks/post-update.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-applypatch.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-commit.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-merge-commit.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-push.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-rebase.sample
Deleted | ERPCRMServer/.git_disabled/hooks/pre-receive.sample
Deleted | ERPCRMServer/.git_disabled/hooks/prepare-commit-msg.sample
Deleted | ERPCRMServer/.git_disabled/hooks/push-to-checkout.sample
Deleted | ERPCRMServer/.git_disabled/hooks/sendemail-validate.sample
Deleted | ERPCRMServer/.git_disabled/hooks/update.sample
Deleted | ERPCRMServer/.git_disabled/index
Deleted | ERPCRMServer/.git_disabled/info/exclude
Deleted | ERPCRMServer/.git_disabled/logs/HEAD
Deleted | ERPCRMServer/.git_disabled/logs/refs/heads/main
Deleted | ERPCRMServer/.git_disabled/logs/refs/remotes/origin/HEAD
Deleted | ERPCRMServer/.git_disabled/objects/pack/pack-4cbb1704c8e62e60367159635adf8e25ce81ca66.idx
Deleted | ERPCRMServer/.git_disabled/objects/pack/pack-4cbb1704c8e62e60367159635adf8e25ce81ca66.pack
Deleted | ERPCRMServer/.git_disabled/objects/pack/pack-4cbb1704c8e62e60367159635adf8e25ce81ca66.rev
Deleted | ERPCRMServer/.git_disabled/packed-refs
Deleted | ERPCRMServer/.git_disabled/refs/heads/main
Deleted | ERPCRMServer/.git_disabled/refs/remotes/origin/HEAD
Modified | ERPCRMServer/Models/System/platformCore.js
Modified | ERPCRMServer/Models/initModels.js
Modified | ERPCRMServer/controllers/InventoryApis/production.js
Modified | ERPCRMServer/controllers/InventoryApis/purchaseReturns.js
Modified | ERPCRMServer/controllers/UserApis/userTypeController.js
Modified | ERPCRMServer/middlewares/rbac.js
Modified | ERPCRMServer/package-lock.json
Modified | ERPCRMServer/package.json
Modified | ERPCRMServer/routes/Inventory/inventoryIndex.js
Modified | ERPCRMServer/routes/System/reportRoutes.js
Modified | ERPCRMServer/server.js
Deleted | clientui/.git_disabled/HEAD
Deleted | clientui/.git_disabled/config
Deleted | clientui/.git_disabled/description
Deleted | clientui/.git_disabled/hooks/applypatch-msg.sample
Deleted | clientui/.git_disabled/hooks/commit-msg.sample
Deleted | clientui/.git_disabled/hooks/fsmonitor-watchman.sample
Deleted | clientui/.git_disabled/hooks/post-update.sample
Deleted | clientui/.git_disabled/hooks/pre-applypatch.sample
Deleted | clientui/.git_disabled/hooks/pre-commit.sample
Deleted | clientui/.git_disabled/hooks/pre-merge-commit.sample
Deleted | clientui/.git_disabled/hooks/pre-push.sample
Deleted | clientui/.git_disabled/hooks/pre-rebase.sample
Deleted | clientui/.git_disabled/hooks/pre-receive.sample
Deleted | clientui/.git_disabled/hooks/prepare-commit-msg.sample
Deleted | clientui/.git_disabled/hooks/push-to-checkout.sample
Deleted | clientui/.git_disabled/hooks/sendemail-validate.sample
Deleted | clientui/.git_disabled/hooks/update.sample
Deleted | clientui/.git_disabled/index
Deleted | clientui/.git_disabled/info/exclude
Deleted | clientui/.git_disabled/logs/HEAD
Deleted | clientui/.git_disabled/logs/refs/heads/main
Deleted | clientui/.git_disabled/logs/refs/remotes/origin/HEAD
Deleted | clientui/.git_disabled/objects/pack/pack-6a6e946139aa6f10c30ae8cc54226a9f1725bcbe.idx
Deleted | clientui/.git_disabled/objects/pack/pack-6a6e946139aa6f10c30ae8cc54226a9f1725bcbe.pack
Deleted | clientui/.git_disabled/objects/pack/pack-6a6e946139aa6f10c30ae8cc54226a9f1725bcbe.rev
Deleted | clientui/.git_disabled/packed-refs
Deleted | clientui/.git_disabled/refs/heads/main
Deleted | clientui/.git_disabled/refs/remotes/origin/HEAD
Modified | clientui/src/Components/AdminSite/CRM/MasterDetails/MasterDetails.jsx
Modified | clientui/src/Components/AdminSite/Modules/ModulesPage.jsx
Modified | clientui/src/Components/AdminSite/NavigationBar/NavigationBar.jsx
Modified | clientui/src/Components/AdminSite/Users/ClassicCorporateOrgChart.jsx
Modified | clientui/src/Components/MainRouting/MainRouting.jsx
Modified | clientui/src/features/crm/pages/MasterDetailsPage.jsx
Modified | clientui/src/features/inventory/pages/finance/PurchaseReturnsPage.jsx
Deleted | task_progress.md
Untracked/New | COMPLETE_API_INVENTORY.xlsx
Untracked/New | CRM_AND_USER_MODULE_GAP_ANALYSIS.md
Untracked/New | ERPCRMServer/FIX_INSTRUCTIONS.md
Untracked/New | ERPCRMServer/Models/InventoryManagement/Accounting.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/CostAdjustment.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/CostingMethod.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/Currencies.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/Documents.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/FinancialYear.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/HSNCode.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/InvoiceMatch.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/LandedCost.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/PriceList.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/RFQ.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/ReorderHistory.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/ReorderLevels.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/StockValuation.js
Untracked/New | ERPCRMServer/Models/InventoryManagement/WarehouseOperations.js
Untracked/New | ERPCRMServer/Models/Users/User2FA.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/accountingController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/advancedReportsController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/currencyController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/documentController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/financialYearController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/hsnCodeController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/invoiceMatchController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/priceListController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/production_fixed.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/reorderLevelController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/rfqController.js
Untracked/New | ERPCRMServer/controllers/InventoryApis/stockValuationController.js
Untracked/New | ERPCRMServer/controllers/auth/twoFactorController.js
Untracked/New | ERPCRMServer/docs/SCHEMA_FIX_REPORT.md
Untracked/New | ERPCRMServer/middleware/hierarchyAccessControl.js
Untracked/New | ERPCRMServer/migrations/URGENT_FIX_DATABASE.sql
Untracked/New | ERPCRMServer/migrations/diagnose_and_fix.sql
Untracked/New | ERPCRMServer/migrations/fix_schema_conflicts.sql
Untracked/New | ERPCRMServer/routes/Auth/twoFactorRoutes.js
Untracked/New | ERPCRMServer/routes/Inventory/accounting/
Untracked/New | ERPCRMServer/routes/Inventory/currency/
Untracked/New | ERPCRMServer/routes/Inventory/documents/
Untracked/New | ERPCRMServer/routes/Inventory/financialYear/
Untracked/New | ERPCRMServer/routes/Inventory/hsnCode/
Untracked/New | ERPCRMServer/routes/Inventory/invoiceMatch/
Untracked/New | ERPCRMServer/routes/Inventory/priceList/
Untracked/New | ERPCRMServer/routes/Inventory/reorderLevels/
Untracked/New | ERPCRMServer/routes/Inventory/rfq/
Untracked/New | ERPCRMServer/routes/Inventory/stockValuation/
Untracked/New | ERPCRMServer/scripts/audit_all_primary_keys.js
Untracked/New | ERPCRMServer/scripts/buildAllModules.js
Untracked/New | ERPCRMServer/scripts/fix_database_schema.js
Untracked/New | ERPCRMServer/scripts/list_all_tables.js
Untracked/New | ERPCRMServer/scripts/verify_schema.js
Untracked/New | ERP_CRM_COMPREHENSIVE_AUDIT.md
Untracked/New | ERP_CRM_Project_Completion_Status.xlsx
Untracked/New | ERP_CRM_Project_Pending_Complete_Detailed.xlsx
Untracked/New | ERP_SYSTEM_GAP_ANALYSIS.md
Untracked/New | IMPLEMENTATION_ROADMAP.md
Untracked/New | IMPLEMENTATION_STATUS.md
Untracked/New | audit/
Untracked/New | clientui/src/Components/AdminSite/UserTypes/
Untracked/New | clientui/src/features/inventory/pages/ChartOfAccountsPage.jsx
Untracked/New | clientui/src/features/inventory/pages/CurrenciesPage.jsx
Untracked/New | clientui/src/features/inventory/pages/DocumentsPage.jsx
Untracked/New | clientui/src/features/inventory/pages/FinancialYearPage.jsx
Untracked/New | clientui/src/features/inventory/pages/HSNCodesPage.jsx
Untracked/New | clientui/src/features/inventory/pages/InvoiceMatchingPage.jsx
Untracked/New | clientui/src/features/inventory/pages/PriceListsPage.jsx
Untracked/New | clientui/src/features/inventory/pages/RFQsPage.jsx
Untracked/New | clientui/src/features/inventory/pages/ReorderLevelsPage.jsx
Untracked/New | clientui/src/features/inventory/pages/StockValuationPage.jsx
Untracked/New | clientui/src/features/inventory/reports/
Untracked/New | create_complete_api_excel.py
Untracked/New | create_project_excel.py
Untracked/New | generate_detailed_project_status_excel.js
Untracked/New | generate_detailed_project_status_excel.py
Untracked/New | testcode/

## Priority Next Actions
Priority | Action | Scope | Reason
P0 | Run backend schema verification | ERPCRMServer/scripts/verify_schema.js | Confirms database fix and new tables.
P0 | Smoke test backend APIs | npm test or Postman collection | Confirms new routes do not break startup/API behavior.
P1 | Validate stock valuation | Stock valuation page and API | High business impact; must verify formulas.
P1 | Validate reorder levels | Reorder levels page and API | High operations impact; confirm min/max and alert logic.
P1 | Validate 2FA login flow | Auth 2FA routes | Security feature must be tested end to end.
P1 | Validate RFQ and invoice matching | RFQ/invoiceMatch routes | Important purchase workflow gap.
P2 | Complete missing WMS workflows | Putaway, picking, cycle count | Needed for advanced warehouse operations.
P2 | Complete reporting gaps | ABC, aging, vendor performance, reconciliation | Needed for management visibility.
P3 | Add external integrations | Email/calendar/SMS/e-commerce/logistics | Useful after core workflows are stable.