## Project Completion Status
ERP/CRM Project Completion Status Report
Generated: 2026-07-22 ¦ Total Features Analyzed: 150+
Module | Feature | Status | Completion % | Priority | Phase | Notes
1. Master Data Management | Item/Product Master | Complete | 100 | High | 1 | Full CRUD with all fields
1. Master Data Management | Item Category / Sub-Category | Complete | 100 | High | 1 | ProductCategories module
1. Master Data Management | Unit of Measurement (UOM) | Complete | 100 | High | 1 | Units module with CRUD
1. Master Data Management | Warehouse/Location Master | Complete | 100 | High | 1 | Warehouses module
1. Master Data Management | Bin/Rack Master | Partial | 50 | Medium | 2 | Basic locations exist
1. Master Data Management | Supplier/Vendor Master | Complete | 100 | High | 1 | Suppliers module
1. Master Data Management | Customer Master | Complete | 100 | High | 1 | Customers module
1. Master Data Management | Brand Master | Complete | 100 | Medium | 1 | Brands module
1. Master Data Management | Item Barcode Setup | Partial | 40 | Low | 3 | Barcode field exists
1. Master Data Management | HSN/SAC Code Master | Not Started | 0 | Medium | 2 | Not implemented
1. Master Data Management | Item Attributes (Size, Color) | Not Started | 0 | Low | 3 | Only Batch/Serial tracked
1. Master Data Management | Item Attributes (Batch, Serial) | Complete | 100 | High | 1 | BatchSerial module
1. Master Data Management | Price List Master | Not Started | 0 | Medium | 2 | Not implemented
1. Master Data Management | Tax Configuration | Complete | 100 | High | 1 | Taxes and ProductTaxMap
2. Purchase Management | Purchase Requisition (PR) | Complete | 100 | High | 1 | PurchaseRequisitions module
2. Purchase Management | Request for Quotation (RFQ) | Not Started | 0 | Medium | 2 | Not implemented
2. Purchase Management | Purchase Order (PO) | Complete | 100 | High | 1 | PurchaseOrders with items
2. Purchase Management | Purchase Order Approval | Partial | 60 | High | 1 | Generic approval system
2. Purchase Management | Goods Receipt Note (GRN) | Complete | 100 | High | 1 | GRN module
2. Purchase Management | Purchase Return / Debit Note | Complete | 100 | High | 1 | PurchaseReturns module
2. Purchase Management | Vendor Bill/Invoice Matching | Not Started | 0 | High | 2 | No 3-way matching
2. Purchase Management | Purchase Order Tracking | Partial | 50 | Medium | 2 | Basic status tracking
2. Purchase Management | Blanket/Contract Orders | Not Started | 0 | Low | 3 | Not implemented
3. Sales & Order Management | Sales Quotation | Complete | 100 | High | 1 | SalesQuotations module
3. Sales & Order Management | Sales Order (SO) | Complete | 100 | High | 1 | SalesOrders module
3. Sales & Order Management | Sales Order Approval | Partial | 60 | High | 1 | Generic approval system
3. Sales & Order Management | Delivery Challan / Dispatch Note | Complete | 100 | High | 1 | DeliveryChallans module
3. Sales & Order Management | Sales Return / Credit Note | Complete | 100 | High | 1 | SalesReturns module
3. Sales & Order Management | Invoice Generation | Complete | 100 | High | 1 | Invoices module (CRM)
3. Sales & Order Management | Backorder Management | Partial | 40 | Medium | 2 | Basic handling only
4. Stock/Inventory Operations | Stock Inward Entry | Complete | 100 | High | 1 | Part of GRN process
4. Stock/Inventory Operations | Stock Outward Entry | Complete | 100 | High | 1 | Part of DeliveryChallan
4. Stock/Inventory Operations | Stock Transfer (Inter-warehouse) | Complete | 100 | High | 1 | StockTransfers module
4. Stock/Inventory Operations | Stock Adjustment (Positive/Negative) | Complete | 100 | High | 1 | StockAdjustments module
4. Stock/Inventory Operations | Stock Reservation/Allocation | Partial | 30 | Medium | 2 | Basic allocation only
4. Stock/Inventory Operations | Batch/Lot Tracking | Complete | 100 | High | 1 | BatchSerial module
4. Stock/Inventory Operations | Serial Number Tracking | Complete | 100 | High | 1 | BatchSerial module
4. Stock/Inventory Operations | Expiry Date Management | Not Started | 0 | Medium | 2 | Not implemented
4. Stock/Inventory Operations | Stock Aging Report | Not Started | 0 | Medium | 2 | Not implemented
4. Stock/Inventory Operations | Reorder Level & Auto Replenishment | Not Started | 0 | High | 1 | Not implemented
4. Stock/Inventory Operations | Min-Max Stock Settings | Not Started | 0 | High | 1 | Not implemented
4. Stock/Inventory Operations | Stock Movements | Complete | 100 | High | 1 | StockMovements module
5. Warehouse Management (WMS) | Bin/Location Mapping | Partial | 50 | Medium | 2 | Basic warehouse locations
5. Warehouse Management (WMS) | Putaway Management | Not Started | 0 | Medium | 3 | Not implemented
5. Warehouse Management (WMS) | Picking List Generation | Not Started | 0 | Medium | 3 | Not implemented
5. Warehouse Management (WMS) | Packing & Shipment | Partial | 40 | Medium | 2 | Basic delivery challan
5. Warehouse Management (WMS) | Cycle Count | Not Started | 0 | Low | 3 | Not implemented
5. Warehouse Management (WMS) | Physical Stock Verification | Not Started | 0 | Low | 3 | Not implemented
5. Warehouse Management (WMS) | Warehouse Transfer Note | Complete | 100 | High | 1 | StockTransfers module
5. Warehouse Management (WMS) | Cross-Docking | Not Started | 0 | Low | 4 | Not implemented
6. Stock Valuation & Costing | Costing Method Setup (FIFO/LIFO/Weighted Avg) | Not Started | 0 | High | 1 | Not implemented
6. Stock Valuation & Costing | Stock Valuation Report | Not Started | 0 | High | 1 | Not implemented
6. Stock Valuation & Costing | Landed Cost Allocation | Not Started | 0 | Medium | 2 | Not implemented
6. Stock Valuation & Costing | Cost Adjustment Entries | Not Started | 0 | Medium | 2 | Not implemented
7. Quality Control | Quality Inspection Setup | Partial | 30 | Medium | 2 | Model exists, not integrated
7. Quality Control | Incoming Inspection (QC on GRN) | Not Started | 0 | Medium | 2 | Not integrated with GRN
7. Quality Control | Rejected/Quarantine Stock | Not Started | 0 | Medium | 2 | Not implemented
7. Quality Control | QC Certificate Management | Not Started | 0 | Low | 3 | Not implemented
8. Production/Manufacturing | Bill of Materials (BOM) | Complete | 100 | High | 1 | BOM module
8. Production/Manufacturing | Material Requisition for Production | Partial | 50 | Medium | 2 | Part of production module
8. Production/Manufacturing | Work Order / Job Card | Complete | 100 | High | 1 | ProductionOrders module
8. Production/Manufacturing | Raw Material Issue | Partial | 50 | Medium | 2 | Part of production module
8. Production/Manufacturing | Finished Goods Receipt | Partial | 50 | Medium | 2 | Part of production module
8. Production/Manufacturing | By-product/Scrap Entry | Not Started | 0 | Low | 3 | Not implemented
9. Reports & Analytics | Stock Summary Report | Partial | 50 | Medium | 2 | Basic reports exist
9. Reports & Analytics | Stock Ledger / Movement Report | Complete | 100 | High | 1 | StockMovements module
9. Reports & Analytics | Stock Valuation Report | Not Started | 0 | High | 1 | Not implemented
9. Reports & Analytics | ABC Analysis | Not Started | 0 | Medium | 3 | Not implemented
9. Reports & Analytics | Slow-Moving/Non-Moving Stock Report | Not Started | 0 | Medium | 3 | Not implemented
9. Reports & Analytics | Reorder Report | Not Started | 0 | High | 1 | Not implemented
9. Reports & Analytics | Vendor Performance Report | Not Started | 0 | Medium | 3 | Not implemented
9. Reports & Analytics | Item-wise Sales & Purchase Analysis | Partial | 60 | Medium | 2 | Basic reporting exists
9. Reports & Analytics | Batch/Serial Traceability Report | Complete | 100 | High | 1 | BatchSerial module
9. Reports & Analytics | Stock Aging Report | Not Started | 0 | Medium | 2 | Not implemented
9. Reports & Analytics | GRN vs PO Reconciliation | Not Started | 0 | Medium | 2 | Not implemented
9. Reports & Analytics | Profit/Loss Reports | Complete | 100 | High | 1 | ProfitLossReports module
10. Utilities & Settings | Barcode/QR Code Generation | Partial | 30 | Low | 3 | Field exists, no UI
10. Utilities & Settings | Import/Export Data (Excel/CSV) | Complete | 100 | High | 1 | DataImportExport module
10. Utilities & Settings | User Role & Permission Setup | Complete | 100 | High | 1 | Full RBAC system
10. Utilities & Settings | Approval Workflow Configuration | Complete | 100 | High | 1 | ApprovalWorkflows tables
10. Utilities & Settings | Audit Trail / Log Management | Complete | 100 | High | 1 | AuditLogs, SecurityLogs
10. Utilities & Settings | Multi-Currency Settings | Not Started | 0 | Medium | 2 | Not implemented
10. Utilities & Settings | Multi-UOM Settings | Partial | 60 | Medium | 2 | Units module exists
10. Utilities & Settings | Tax Configuration (GST/VAT) | Complete | 100 | High | 1 | Taxes module
10. Utilities & Settings | Financial Year/Period Settings | Not Started | 0 | Medium | 2 | Not implemented
11. Integration Modules | Finance/Accounting Integration | Partial | 20 | High | 2 | Basic expenses only
11. Integration Modules | CRM Integration | Complete | 100 | High | 1 | Full CRM integration
11. Integration Modules | E-commerce/Marketplace Sync | Not Started | 0 | Low | 4 | Not implemented
11. Integration Modules | Logistics/Shipping Integration | Not Started | 0 | Low | 4 | Not implemented
11. Integration Modules | Barcode Scanner/RFID Integration | Not Started | 0 | Low | 4 | Not implemented
12. CRM - Core Entities | Leads Management | Complete | 100 | High | 1 | Full leads module
12. CRM - Core Entities | Opportunities Management | Complete | 100 | High | 1 | Full opportunities module
12. CRM - Core Entities | Accounts Management | Complete | 100 | High | 1 | Full accounts module
12. CRM - Core Entities | Contacts Management | Complete | 100 | High | 1 | Full contacts module
12. CRM - Core Entities | Activities Management | Complete | 100 | High | 1 | Full activities module
12. CRM - Core Entities | Cases/Support Tickets | Complete | 100 | High | 1 | Full cases module
12. CRM - Core Entities | Quotes Management | Complete | 100 | High | 1 | Full quotes module
12. CRM - Core Entities | Invoices Management | Complete | 100 | High | 1 | Full invoices module
12. CRM - Core Entities | Payments Management | Complete | 100 | High | 1 | Full payments module
12. CRM - Core Entities | Retentions/Follow-ups | Complete | 100 | Medium | 1 | Full retentions module
12. CRM - Core Entities | Presales Management | Partial | 70 | Medium | 2 | Model exists, UI partial
13. CRM - Master Data | Lead Sources | Complete | 100 | High | 1 | LeadSources master
13. CRM - Master Data | Industries | Complete | 100 | Medium | 1 | Industries master
13. CRM - Master Data | Sales Stages | Complete | 100 | High | 1 | SalesStages master
13. CRM - Master Data | Follow-up Types | Complete | 100 | Medium | 1 | FollowupTypes master
13. CRM - Master Data | Task Types | Complete | 100 | Medium | 1 | TaskTypes master
13. CRM - Master Data | Payment Terms Master | Not Started | 0 | Medium | 2 | Not implemented
13. CRM - Master Data | Case Types/Categories | Not Started | 0 | Low | 3 | Not implemented
14. CRM - Workflows | Lead-to-Opportunity Conversion | Complete | 100 | High | 1 | Implemented
14. CRM - Workflows | Opportunity-to-Quote Conversion | Complete | 100 | High | 1 | Implemented
14. CRM - Workflows | Quote-to-Invoice Conversion | Complete | 100 | High | 1 | Implemented
14. CRM - Workflows | Invoice-to-Payment Tracking | Complete | 100 | High | 1 | Implemented
14. CRM - Workflows | Visual Workflow Builder | Not Started | 0 | Medium | 3 | Not implemented
14. CRM - Workflows | Automated Email Notifications | Not Started | 0 | Medium | 2 | Not implemented
14. CRM - Workflows | SLA Management | Not Started | 0 | Low | 3 | Not implemented
15. CRM - Reports & Analytics | Lead Reports | Complete | 100 | High | 1 | Basic reports
15. CRM - Reports & Analytics | Opportunity Reports | Complete | 100 | High | 1 | Basic reports
15. CRM - Reports & Analytics | Sales Pipeline Dashboard | Complete | 100 | High | 1 | Dashboard exists
15. CRM - Reports & Analytics | Conversion Rate Analytics | Not Started | 0 | Medium | 2 | Not implemented
15. CRM - Reports & Analytics | Sales Forecasting | Not Started | 0 | Medium | 2 | Not implemented
15. CRM - Reports & Analytics | Lead Source Effectiveness | Not Started | 0 | Low | 3 | Not implemented
15. CRM - Reports & Analytics | Custom Report Builder | Not Started | 0 | Low | 3 | Not implemented
16. CRM - Integration | Email Integration | Not Started | 0 | High | 2 | Not implemented
16. CRM - Integration | Calendar Integration | Not Started | 0 | Medium | 2 | Not implemented
16. CRM - Integration | Document Management | Not Started | 0 | Medium | 2 | Not implemented
16. CRM - Integration | Customer Portal | Not Started | 0 | Low | 3 | Not implemented
16. CRM - Integration | Social Media Integration | Not Started | 0 | Low | 4 | Not implemented
17. User Management | User Registration | Complete | 100 | High | 1 | RegisterUserPage
17. User Management | User Profile Management | Complete | 100 | High | 1 | Profile pages
17. User Management | User Listing & Search | Complete | 100 | High | 1 | UsersPage
17. User Management | User Activation/Deactivation | Complete | 100 | High | 1 | IsActive flag
17. User Management | Profile Image Upload | Complete | 100 | Medium | 1 | Implemented
17. User Management | User Impersonation | Not Started | 0 | Medium | 2 | Not implemented
17. User Management | User Activity Tracking | Not Started | 0 | Low | 3 | Not implemented
17. User Management | Bulk User Import | Partial | 40 | Medium | 2 | Basic import exists
18. Role Management | Role Creation & Management | Complete | 100 | High | 1 | Roles module
18. Role Management | Role Assignment to Users | Complete | 100 | High | 1 | RoleId in Users
18. Role Management | Predefined Roles | Complete | 100 | High | 1 | Owner, Manager, etc.
18. Role Management | Role Cloning/Duplication | Not Started | 0 | Low | 3 | Not implemented
18. Role Management | Role Hierarchy | Not Started | 0 | Low | 3 | Not implemented
18. Role Management | Role Templates | Not Started | 0 | Low | 3 | Not implemented
19. Permission Management | Permission Structure | Complete | 100 | High | 1 | Permissions table
19. Permission Management | Role-Level Permissions | Complete | 100 | High | 1 | RolePermissions table
19. Permission Management | User-Level Permissions | Complete | 100 | High | 1 | UserPermissions table
19. Permission Management | Field-Level Permissions | Not Started | 0 | High | 2 | Not implemented
19. Permission Management | Record-Level Permissions | Not Started | 0 | High | 2 | Not implemented
19. Permission Management | Time-Based Permissions | Not Started | 0 | Low | 3 | Not implemented
19. Permission Management | Permission Delegation | Not Started | 0 | Low | 3 | Not implemented
20. Authentication & Security | Email/Password Authentication | Complete | 100 | High | 1 | JWT-based
20. Authentication & Security | JWT Token Authentication | Complete | 100 | High | 1 | Implemented
20. Authentication & Security | Refresh Token Mechanism | Complete | 100 | High | 1 | Implemented
20. Authentication & Security | Email Verification | Complete | 100 | High | 1 | With tokens
20. Authentication & Security | Password Reset | Complete | 100 | High | 1 | With expiration
20. Authentication & Security | Account Locking | Complete | 100 | High | 1 | Brute-force protection
20. Authentication & Security | Two-Factor Authentication (2FA) | Not Started | 0 | High | 2 | Not implemented
20. Authentication & Security | OAuth Integration | Not Started | 0 | Medium | 2 | Not implemented
20. Authentication & Security | SSO/SAML Integration | Not Started | 0 | Medium | 2 | Not implemented
20. Authentication & Security | LDAP/AD Integration | Not Started | 0 | Medium | 2 | Not implemented
20. Authentication & Security | Password Strength Enforcement | Not Started | 0 | Medium | 2 | Not implemented
20. Authentication & Security | Password History | Not Started | 0 | Low | 3 | Not implemented
21. Audit & Compliance | Audit Trail | Complete | 100 | High | 1 | AuditLogs table
21. Audit & Compliance | Security Logs | Complete | 100 | High | 1 | SecurityLogs table
21. Audit & Compliance | Login/Logout Tracking | Complete | 100 | High | 1 | Implemented
21. Audit & Compliance | Entity-Level Audit Fields | Complete | 100 | High | 1 | CreatedBy, UpdatedBy
21. Audit & Compliance | Detailed Change Tracking | Not Started | 0 | Medium | 2 | Before/after values
21. Audit & Compliance | Audit Log Search & Filter | Not Started | 0 | Medium | 2 | Not implemented
21. Audit & Compliance | GDPR Compliance Tools | Not Started | 0 | Medium | 2 | Not implemented
21. Audit & Compliance | Data Retention Policies | Not Started | 0 | Low | 3 | Not implemented
22. Notifications | In-App Notifications | Complete | 100 | High | 1 | Notifications table
22. Notifications | Notification Preferences | Complete | 100 | Medium | 1 | Preferences exist
22. Notifications | Email Notifications | Not Started | 0 | Medium | 2 | Not implemented
22. Notifications | SMS Notifications | Not Started | 0 | Low | 3 | Not implemented
22. Notifications | Push Notifications | Not Started | 0 | Low | 3 | Not implemented
22. Notifications | Real-Time Notifications | Not Started | 0 | Medium | 2 | WebSocket not implemented
SUMMARY STATISTICS
Total Features | 174
Complete | 82 | 47.1%
Partial | 20 | 11.5%
Not Started | 72 | 41.4%
Overall Completion (Weighted) |  | 52.9%
Remaining Work |  | 47.1%
MODULE-WISE COMPLETION
Module | Total Features | Complete | Partial | Not Started | Completion % | Status
1. Master Data Management | 14 | 9 | 2 | 3 | 71.4% | Partial
2. Purchase Management | 9 | 4 | 2 | 3 | 55.6% | Partial
3. Sales & Order Management | 7 | 5 | 2 | 0 | 85.7% | Partial
4. Stock/Inventory Operations | 12 | 7 | 1 | 4 | 62.5% | Partial
5. Warehouse Management (WMS) | 8 | 1 | 2 | 5 | 25.0% | Partial
6. Stock Valuation & Costing | 4 | 0 | 0 | 4 | 0.0% | Not Started
7. Quality Control | 4 | 0 | 1 | 3 | 12.5% | Partial
8. Production/Manufacturing | 6 | 2 | 3 | 1 | 58.3% | Partial
9. Reports & Analytics | 12 | 3 | 2 | 7 | 33.3% | Partial
10. Utilities & Settings | 9 | 5 | 2 | 2 | 66.7% | Partial
11. Integration Modules | 5 | 1 | 1 | 3 | 30.0% | Partial
12. CRM - Core Entities | 11 | 10 | 1 | 0 | 95.5% | Partial
13. CRM - Master Data | 7 | 5 | 0 | 2 | 71.4% | Partial
14. CRM - Workflows | 7 | 4 | 0 | 3 | 57.1% | Partial
15. CRM - Reports & Analytics | 7 | 3 | 0 | 4 | 42.9% | Partial
16. CRM - Integration | 5 | 0 | 0 | 5 | 0.0% | Not Started
17. User Management | 8 | 5 | 1 | 2 | 68.8% | Partial
18. Role Management | 6 | 3 | 0 | 3 | 50.0% | Partial
19. Permission Management | 7 | 3 | 0 | 4 | 42.9% | Partial
20. Authentication & Security | 12 | 6 | 0 | 6 | 50.0% | Partial
21. Audit & Compliance | 8 | 4 | 0 | 4 | 50.0% | Partial
22. Notifications | 6 | 2 | 0 | 4 | 33.3% | Partial