## Feature Status
ERP/CRM Project - Done & Pending Work Tracker
Generated: 2026-07-24 | Total: 174 | Completed: 82 | Partial: 20 | Not Started: 72 | Completion: 52.9%
# | Module | Feature | Status | Completion % | Priority | Category | Notes
1 | 1. Master Data Management | Item/Product Master | COMPLETED | 100 | High | Done | Full CRUD with all fields
2 | 1. Master Data Management | Item Category / Sub-Category | COMPLETED | 100 | High | Done | ProductCategories module
3 | 1. Master Data Management | Unit of Measurement (UOM) | COMPLETED | 100 | High | Done | Units module with CRUD
4 | 1. Master Data Management | Warehouse/Location Master | COMPLETED | 100 | High | Done | Warehouses module
5 | 1. Master Data Management | Supplier/Vendor Master | COMPLETED | 100 | High | Done | Suppliers module
6 | 1. Master Data Management | Customer Master | COMPLETED | 100 | High | Done | Customers module
7 | 1. Master Data Management | Brand Master | COMPLETED | 100 | Medium | Done | Brands module
8 | 1. Master Data Management | Item Attributes (Batch, Serial) | COMPLETED | 100 | High | Done | BatchSerial module
9 | 1. Master Data Management | Tax Configuration | COMPLETED | 100 | High | Done | Taxes and ProductTaxMap
10 | 1. Master Data Management | Bin/Rack Master | PARTIAL | 50 | Medium | Partial-Complete | Basic locations exist
11 | 1. Master Data Management | Item Barcode Setup | PARTIAL | 40 | Low | Partial-Complete | Barcode field exists
12 | 1. Master Data Management | HSN/SAC Code Master | NOT STARTED | 0 | Medium | Pending | Not implemented
13 | 1. Master Data Management | Item Attributes (Size, Color) | NOT STARTED | 0 | Low | Pending | Only Batch/Serial tracked
14 | 1. Master Data Management | Price List Master | NOT STARTED | 0 | Medium | Pending | Not implemented
15 | 2. Purchase Management | Purchase Requisition (PR) | COMPLETED | 100 | High | Done | PurchaseRequisitions module
16 | 2. Purchase Management | Purchase Order (PO) | COMPLETED | 100 | High | Done | PurchaseOrders with items
17 | 2. Purchase Management | Goods Receipt Note (GRN) | COMPLETED | 100 | High | Done | GRN module
18 | 2. Purchase Management | Purchase Return / Debit Note | COMPLETED | 100 | High | Done | PurchaseReturns module
19 | 2. Purchase Management | Purchase Order Approval | PARTIAL | 60 | High | Partial-Complete | Generic approval system
20 | 2. Purchase Management | Purchase Order Tracking | PARTIAL | 50 | Medium | Partial-Complete | Basic status tracking
21 | 2. Purchase Management | Request for Quotation (RFQ) | NOT STARTED | 0 | Medium | Pending | Not implemented
22 | 2. Purchase Management | Vendor Bill/Invoice Matching | NOT STARTED | 0 | High | Pending | No 3-way matching
23 | 2. Purchase Management | Blanket/Contract Orders | NOT STARTED | 0 | Low | Pending | Not implemented
24 | 3. Sales & Order Management | Sales Quotation | COMPLETED | 100 | High | Done | SalesQuotations module
25 | 3. Sales & Order Management | Sales Order (SO) | COMPLETED | 100 | High | Done | SalesOrders module
26 | 3. Sales & Order Management | Sales Order Approval | PARTIAL | 60 | High | Partial-Complete | Generic approval system
27 | 3. Sales & Order Management | Delivery Challan / Dispatch Note | COMPLETED | 100 | High | Done | DeliveryChallans module
28 | 3. Sales & Order Management | Sales Return / Credit Note | COMPLETED | 100 | High | Done | SalesReturns module
29 | 3. Sales & Order Management | Invoice Generation | COMPLETED | 100 | High | Done | Invoices module (CRM)
30 | 3. Sales & Order Management | Backorder Management | PARTIAL | 40 | Medium | Partial-Complete | Basic handling only
31 | 4. Stock/Inventory Operations | Stock Inward Entry | COMPLETED | 100 | High | Done | Part of GRN process
32 | 4. Stock/Inventory Operations | Stock Outward Entry | COMPLETED | 100 | High | Done | Part of DeliveryChallan
33 | 4. Stock/Inventory Operations | Stock Transfer (Inter-warehouse) | COMPLETED | 100 | High | Done | StockTransfers module
34 | 4. Stock/Inventory Operations | Stock Adjustment (Positive/Negative) | COMPLETED | 100 | High | Done | StockAdjustments module
35 | 4. Stock/Inventory Operations | Batch/Lot Tracking | COMPLETED | 100 | High | Done | BatchSerial module
36 | 4. Stock/Inventory Operations | Serial Number Tracking | COMPLETED | 100 | High | Done | BatchSerial module
37 | 4. Stock/Inventory Operations | Stock Movements | COMPLETED | 100 | High | Done | StockMovements module
38 | 4. Stock/Inventory Operations | Stock Reservation/Allocation | PARTIAL | 30 | Medium | Partial-Complete | Basic allocation only
39 | 4. Stock/Inventory Operations | Expiry Date Management | NOT STARTED | 0 | Medium | Pending | Not implemented
40 | 4. Stock/Inventory Operations | Stock Aging Report | NOT STARTED | 0 | Medium | Pending | Not implemented
41 | 4. Stock/Inventory Operations | Reorder Level & Auto Replenishment | NOT STARTED | 0 | High | Pending | Not implemented
42 | 4. Stock/Inventory Operations | Min-Max Stock Settings | NOT STARTED | 0 | High | Pending | Not implemented
43 | 5. Warehouse Management (WMS) | Bin/Location Mapping | PARTIAL | 50 | Medium | Partial-Complete | Basic warehouse locations
44 | 5. Warehouse Management (WMS) | Warehouse Transfer Note | COMPLETED | 100 | High | Done | StockTransfers module
45 | 5. Warehouse Management (WMS) | Packing & Shipment | PARTIAL | 40 | Medium | Partial-Complete | Basic delivery challan
46 | 5. Warehouse Management (WMS) | Putaway Management | NOT STARTED | 0 | Low | Pending | Not implemented
47 | 5. Warehouse Management (WMS) | Picking List Generation | NOT STARTED | 0 | Low | Pending | Not implemented
48 | 5. Warehouse Management (WMS) | Cycle Count | NOT STARTED | 0 | Low | Pending | Not implemented
49 | 5. Warehouse Management (WMS) | Physical Stock Verification | NOT STARTED | 0 | Low | Pending | Not implemented
50 | 5. Warehouse Management (WMS) | Cross-Docking | NOT STARTED | 0 | Low | Pending | Not implemented
51 | 6. Stock Valuation & Costing | Costing Method Setup | NOT STARTED | 0 | High | Pending | Not implemented
52 | 6. Stock Valuation & Costing | Stock Valuation Report | NOT STARTED | 0 | High | Pending | Not implemented
53 | 6. Stock Valuation & Costing | Landed Cost Allocation | NOT STARTED | 0 | Medium | Pending | Not implemented
54 | 6. Stock Valuation & Costing | Cost Adjustment Entries | NOT STARTED | 0 | Medium | Pending | Not implemented
55 | 7. Quality Control | Quality Inspection Setup | PARTIAL | 30 | Medium | Partial-Complete | Model exists, not integrated
56 | 7. Quality Control | Incoming Inspection (QC on GRN) | NOT STARTED | 0 | Medium | Pending | Not integrated with GRN
57 | 7. Quality Control | Rejected/Quarantine Stock | NOT STARTED | 0 | Medium | Pending | Not implemented
58 | 7. Quality Control | QC Certificate Management | NOT STARTED | 0 | Low | Pending | Not implemented
59 | 8. Production/Manufacturing | Bill of Materials (BOM) | COMPLETED | 100 | High | Done | BOM module
60 | 8. Production/Manufacturing | Work Order / Job Card | COMPLETED | 100 | High | Done | ProductionOrders module
61 | 8. Production/Manufacturing | Material Requisition for Production | PARTIAL | 50 | Medium | Partial-Complete | Part of production module
62 | 8. Production/Manufacturing | Raw Material Issue | PARTIAL | 50 | Medium | Partial-Complete | Part of production module
63 | 8. Production/Manufacturing | Finished Goods Receipt | PARTIAL | 50 | Medium | Partial-Complete | Part of production module
64 | 8. Production/Manufacturing | By-product/Scrap Entry | NOT STARTED | 0 | Low | Pending | Not implemented
65 | 9. Reports & Analytics | Stock Ledger / Movement Report | COMPLETED | 100 | High | Done | StockMovements module
66 | 9. Reports & Analytics | Batch/Serial Traceability Report | COMPLETED | 100 | High | Done | BatchSerial module
67 | 9. Reports & Analytics | Profit/Loss Reports | COMPLETED | 100 | High | Done | ProfitLossReports module
68 | 9. Reports & Analytics | Stock Summary Report | PARTIAL | 50 | Medium | Partial-Complete | Basic reports exist
69 | 9. Reports & Analytics | Item-wise Sales & Purchase Analysis | PARTIAL | 60 | Medium | Partial-Complete | Basic reporting exists
70 | 9. Reports & Analytics | Stock Valuation Report | NOT STARTED | 0 | High | Pending | Not implemented
71 | 9. Reports & Analytics | ABC Analysis | NOT STARTED | 0 | Medium | Pending | Not implemented
72 | 9. Reports & Analytics | Slow-Moving/Non-Moving Stock Report | NOT STARTED | 0 | Medium | Pending | Not implemented
73 | 9. Reports & Analytics | Reorder Report | NOT STARTED | 0 | High | Pending | Not implemented
74 | 9. Reports & Analytics | Vendor Performance Report | NOT STARTED | 0 | Medium | Pending | Not implemented
75 | 9. Reports & Analytics | Stock Aging Report | NOT STARTED | 0 | Medium | Pending | Not implemented
76 | 9. Reports & Analytics | GRN vs PO Reconciliation | NOT STARTED | 0 | Medium | Pending | Not implemented
77 | 10. Utilities & Settings | Import/Export Data (Excel/CSV) | COMPLETED | 100 | High | Done | DataImportExport module
78 | 10. Utilities & Settings | User Role & Permission Setup | COMPLETED | 100 | High | Done | Full RBAC system
79 | 10. Utilities & Settings | Approval Workflow Configuration | COMPLETED | 100 | High | Done | ApprovalWorkflows tables
80 | 10. Utilities & Settings | Audit Trail / Log Management | COMPLETED | 100 | High | Done | AuditLogs, SecurityLogs
81 | 10. Utilities & Settings | Tax Configuration (GST/VAT) | COMPLETED | 100 | High | Done | Taxes module
82 | 10. Utilities & Settings | Multi-UOM Settings | PARTIAL | 60 | Medium | Partial-Complete | Units module exists
83 | 10. Utilities & Settings | Barcode/QR Code Generation | PARTIAL | 30 | Low | Partial-Complete | Field exists, no UI
84 | 10. Utilities & Settings | Multi-Currency Settings | NOT STARTED | 0 | Medium | Pending | Not implemented
85 | 10. Utilities & Settings | Financial Year/Period Settings | NOT STARTED | 0 | Medium | Pending | Not implemented
86 | 11. Integration Modules | CRM Integration | COMPLETED | 100 | High | Done | Full CRM integration
87 | 11. Integration Modules | Finance/Accounting Integration | PARTIAL | 20 | High | Partial-Complete | Basic expenses only
88 | 11. Integration Modules | E-commerce/Marketplace Sync | NOT STARTED | 0 | Low | Pending | Not implemented
89 | 11. Integration Modules | Logistics/Shipping Integration | NOT STARTED | 0 | Low | Pending | Not implemented
90 | 11. Integration Modules | Barcode Scanner/RFID Integration | NOT STARTED | 0 | Low | Pending | Not implemented
91 | 12. CRM - Core Entities | Leads Management | COMPLETED | 100 | High | Done | Full leads module
92 | 12. CRM - Core Entities | Opportunities Management | COMPLETED | 100 | High | Done | Full opportunities module
93 | 12. CRM - Core Entities | Accounts Management | COMPLETED | 100 | High | Done | Full accounts module
94 | 12. CRM - Core Entities | Contacts Management | COMPLETED | 100 | High | Done | Full contacts module
95 | 12. CRM - Core Entities | Activities Management | COMPLETED | 100 | High | Done | Full activities module
96 | 12. CRM - Core Entities | Cases/Support Tickets | COMPLETED | 100 | High | Done | Full cases module
97 | 12. CRM - Core Entities | Quotes Management | COMPLETED | 100 | High | Done | Full quotes module
98 | 12. CRM - Core Entities | Invoices Management | COMPLETED | 100 | High | Done | Full invoices module
99 | 12. CRM - Core Entities | Payments Management | COMPLETED | 100 | High | Done | Full payments module
100 | 12. CRM - Core Entities | Retentions/Follow-ups | COMPLETED | 100 | Medium | Done | Full retentions module
101 | 12. CRM - Core Entities | Presales Management | PARTIAL | 70 | Medium | Partial-Complete | Model exists, UI partial
102 | 13. CRM - Master Data | Lead Sources | COMPLETED | 100 | High | Done | LeadSources master
103 | 13. CRM - Master Data | Industries | COMPLETED | 100 | Medium | Done | Industries master
104 | 13. CRM - Master Data | Sales Stages | COMPLETED | 100 | High | Done | SalesStages master
105 | 13. CRM - Master Data | Follow-up Types | COMPLETED | 100 | Medium | Done | FollowupTypes master
106 | 13. CRM - Master Data | Task Types | COMPLETED | 100 | Medium | Done | TaskTypes master
107 | 13. CRM - Master Data | Payment Terms Master | NOT STARTED | 0 | Medium | Pending | Not implemented
108 | 13. CRM - Master Data | Case Types/Categories | NOT STARTED | 0 | Low | Pending | Not implemented
109 | 14. CRM - Workflows | Lead-to-Opportunity Conversion | COMPLETED | 100 | High | Done | Implemented
110 | 14. CRM - Workflows | Opportunity-to-Quote Conversion | COMPLETED | 100 | High | Done | Implemented
111 | 14. CRM - Workflows | Quote-to-Invoice Conversion | COMPLETED | 100 | High | Done | Implemented
112 | 14. CRM - Workflows | Invoice-to-Payment Tracking | COMPLETED | 100 | High | Done | Implemented
113 | 14. CRM - Workflows | Visual Workflow Builder | NOT STARTED | 0 | Medium | Pending | Not implemented
114 | 14. CRM - Workflows | Automated Email Notifications | NOT STARTED | 0 | Medium | Pending | Not implemented
115 | 14. CRM - Workflows | SLA Management | NOT STARTED | 0 | Low | Pending | Not implemented
116 | 15. CRM - Reports & Analytics | Lead Reports | COMPLETED | 100 | High | Done | Basic reports
117 | 15. CRM - Reports & Analytics | Opportunity Reports | COMPLETED | 100 | High | Done | Basic reports
118 | 15. CRM - Reports & Analytics | Sales Pipeline Dashboard | COMPLETED | 100 | High | Done | Dashboard exists
119 | 15. CRM - Reports & Analytics | Conversion Rate Analytics | NOT STARTED | 0 | Medium | Pending | Not implemented
120 | 15. CRM - Reports & Analytics | Sales Forecasting | NOT STARTED | 0 | Medium | Pending | Not implemented
121 | 15. CRM - Reports & Analytics | Lead Source Effectiveness | NOT STARTED | 0 | Low | Pending | Not implemented
122 | 15. CRM - Reports & Analytics | Custom Report Builder | NOT STARTED | 0 | Low | Pending | Not implemented
123 | 16. CRM - Integration | Email Integration | NOT STARTED | 0 | High | Pending | Not implemented
124 | 16. CRM - Integration | Calendar Integration | NOT STARTED | 0 | Medium | Pending | Not implemented
125 | 16. CRM - Integration | Document Management | NOT STARTED | 0 | Medium | Pending | Not implemented
126 | 16. CRM - Integration | Customer Portal | NOT STARTED | 0 | Low | Pending | Not implemented
127 | 16. CRM - Integration | Social Media Integration | NOT STARTED | 0 | Low | Pending | Not implemented
128 | 17. User Management | User Registration | COMPLETED | 100 | High | Done | RegisterUserPage
129 | 17. User Management | User Profile Management | COMPLETED | 100 | High | Done | Profile pages
130 | 17. User Management | User Listing & Search | COMPLETED | 100 | High | Done | UsersPage
131 | 17. User Management | User Activation/Deactivation | COMPLETED | 100 | High | Done | IsActive flag
132 | 17. User Management | Profile Image Upload | COMPLETED | 100 | Medium | Done | Implemented
133 | 17. User Management | Bulk User Import | PARTIAL | 40 | Medium | Partial-Complete | Basic import exists
134 | 17. User Management | User Impersonation | NOT STARTED | 0 | Medium | Pending | Not implemented
135 | 17. User Management | User Activity Tracking | NOT STARTED | 0 | Low | Pending | Not implemented
136 | 18. Role Management | Role Creation & Management | COMPLETED | 100 | High | Done | Roles module
137 | 18. Role Management | Role Assignment to Users | COMPLETED | 100 | High | Done | RoleId in Users
138 | 18. Role Management | Predefined Roles | COMPLETED | 100 | High | Done | Owner, Manager, etc.
139 | 18. Role Management | Role Cloning/Duplication | NOT STARTED | 0 | Low | Pending | Not implemented
140 | 18. Role Management | Role Hierarchy | NOT STARTED | 0 | Low | Pending | Not implemented
141 | 18. Role Management | Role Templates | NOT STARTED | 0 | Low | Pending | Not implemented
142 | 19. Permission Management | Permission Structure | COMPLETED | 100 | High | Done | Permissions table
143 | 19. Permission Management | Role-Level Permissions | COMPLETED | 100 | High | Done | RolePermissions table
144 | 19. Permission Management | User-Level Permissions | COMPLETED | 100 | High | Done | UserPermissions table
145 | 19. Permission Management | Field-Level Permissions | NOT STARTED | 0 | High | Pending | Not implemented
146 | 19. Permission Management | Record-Level Permissions | NOT STARTED | 0 | High | Pending | Not implemented
147 | 19. Permission Management | Time-Based Permissions | NOT STARTED | 0 | Low | Pending | Not implemented
148 | 19. Permission Management | Permission Delegation | NOT STARTED | 0 | Low | Pending | Not implemented
149 | 20. Authentication & Security | Email/Password Authentication | COMPLETED | 100 | High | Done | JWT-based
150 | 20. Authentication & Security | JWT Token Authentication | COMPLETED | 100 | High | Done | Implemented
151 | 20. Authentication & Security | Refresh Token Mechanism | COMPLETED | 100 | High | Done | Implemented
152 | 20. Authentication & Security | Email Verification | COMPLETED | 100 | High | Done | With tokens
153 | 20. Authentication & Security | Password Reset | COMPLETED | 100 | High | Done | With expiration
154 | 20. Authentication & Security | Account Locking | COMPLETED | 100 | High | Done | Brute-force protection
155 | 20. Authentication & Security | Two-Factor Authentication (2FA) | NOT STARTED | 0 | High | Pending | Not implemented
156 | 20. Authentication & Security | OAuth Integration | NOT STARTED | 0 | Medium | Pending | Not implemented
157 | 20. Authentication & Security | SSO/SAML Integration | NOT STARTED | 0 | Medium | Pending | Not implemented
158 | 20. Authentication & Security | LDAP/AD Integration | NOT STARTED | 0 | Medium | Pending | Not implemented
159 | 20. Authentication & Security | Password Strength Enforcement | NOT STARTED | 0 | Medium | Pending | Not implemented
160 | 20. Authentication & Security | Password History | NOT STARTED | 0 | Low | Pending | Not implemented
161 | 21. Audit & Compliance | Audit Trail | COMPLETED | 100 | High | Done | AuditLogs table
162 | 21. Audit & Compliance | Security Logs | COMPLETED | 100 | High | Done | SecurityLogs table
163 | 21. Audit & Compliance | Login/Logout Tracking | COMPLETED | 100 | High | Done | Implemented
164 | 21. Audit & Compliance | Entity-Level Audit Fields | COMPLETED | 100 | High | Done | CreatedBy, UpdatedBy
165 | 21. Audit & Compliance | Detailed Change Tracking | NOT STARTED | 0 | Medium | Pending | Before/after values
166 | 21. Audit & Compliance | Audit Log Search & Filter | NOT STARTED | 0 | Medium | Pending | Not implemented
167 | 21. Audit & Compliance | GDPR Compliance Tools | NOT STARTED | 0 | Medium | Pending | Not implemented
168 | 21. Audit & Compliance | Data Retention Policies | NOT STARTED | 0 | Low | Pending | Not implemented
169 | 22. Notifications | In-App Notifications | COMPLETED | 100 | High | Done | Notifications table
170 | 22. Notifications | Notification Preferences | COMPLETED | 100 | Medium | Done | Preferences exist
171 | 22. Notifications | Email Notifications | NOT STARTED | 0 | Medium | Pending | Not implemented
172 | 22. Notifications | SMS Notifications | NOT STARTED | 0 | Low | Pending | Not implemented
173 | 22. Notifications | Push Notifications | NOT STARTED | 0 | Low | Pending | Not implemented
174 | 22. Notifications | Real-Time Notifications | NOT STARTED | 0 | Medium | Pending | WebSocket not implemented

## Partial - To Complete
PARTIALLY IMPLEMENTED FEATURES - REQUIRE COMPLETION
# | Module | Feature | Completion % | Current Status | What Needs To Be Done
1 | 1. Master Data Management | Bin/Rack Master | 50 | Basic locations exist | Dedicated bin/rack management module, assign bins to products
2 | 1. Master Data Management | Item Barcode Setup | 40 | Barcode field exists | Barcode generation logic, barcode printing UI, barcode scanning support
3 | 2. Purchase Management | Purchase Order Approval | 60 | Generic approval system | PO-specific approval workflow, multi-level approval, approval notifications
4 | 2. Purchase Management | Purchase Order Tracking | 50 | Basic status tracking | Detailed tracking, shipment tracking, ETA, timeline view
5 | 3. Sales & Order Management | Sales Order Approval | 60 | Generic approval system | SO-specific approval workflow, credit limit check, multi-level approval
6 | 3. Sales & Order Management | Backorder Management | 40 | Basic handling only | Backorder creation, allocation, partial shipment, backorder reports
7 | 4. Stock/Inventory Operations | Stock Reservation/Allocation | 30 | Basic allocation only | Dedicated reservation system, allocate against SO/PO, release logic
8 | 5. Warehouse Management (WMS) | Bin/Location Mapping | 50 | Basic warehouse locations | Detailed bin mapping, zone mapping, putaway rules, picking strategies
9 | 5. Warehouse Management (WMS) | Packing & Shipment | 40 | Basic delivery challan | Packing list generation, carrier integration, shipment tracking, label printing
10 | 7. Quality Control | Quality Inspection Setup | 30 | Model exists, not integrated | Integration with GRN, inspection checklist, pass/fail logic, quarantine
11 | 8. Production/Manufacturing | Material Requisition for Production | 50 | Part of production module | Separate requisition workflow, approval, against WO, tracking
12 | 8. Production/Manufacturing | Raw Material Issue | 50 | Part of production module | Dedicated issue workflow, batch picking, cost calculation
13 | 8. Production/Manufacturing | Finished Goods Receipt | 50 | Part of production module | QC integration, receipt against WO, automatic inventory update
14 | 9. Reports & Analytics | Stock Summary Report | 50 | Basic reports exist | Enhanced filters, export, drill-down, warehouse-wise
15 | 9. Reports & Analytics | Item-wise Sales & Purchase Analysis | 60 | Basic reporting exists | Advanced filters, trends, comparison, export
16 | 10. Utilities & Settings | Multi-UOM Settings | 60 | Units module exists | UOM conversion rules, auto-conversion on transactions
17 | 10. Utilities & Settings | Barcode/QR Code Generation | 30 | Field exists, no UI | Generation service, print templates, scanning integration
18 | 11. Integration Modules | Finance/Accounting Integration | 20 | Basic expenses only | Full accounting integration, journal entries, chart of accounts
19 | 12. CRM - Core Entities | Presales Management | 70 | Model exists, UI partial | Complete UI, presales workflow, demo scheduling
20 | 17. User Management | Bulk User Import | 40 | Basic import exists | Validation, templates, error reporting, role assignment

## Pending - Not Started
NOT STARTED FEATURES - PENDING IMPLEMENTATION
# | Module | Feature | Phase | Priority | Est. Effort
1 | 6. Stock Valuation & Costing | Costing Method Setup (FIFO/LIFO) | 1-Critical Core | HIGH | 3-4 weeks
2 | 6. Stock Valuation & Costing | Stock Valuation Report | 1-Critical Core | HIGH | 2-3 weeks
3 | 6. Stock Valuation & Costing | Landed Cost Allocation | 1-Critical Core | MEDIUM | 3-4 weeks
4 | 6. Stock Valuation & Costing | Cost Adjustment Entries | 1-Critical Core | MEDIUM | 2-3 weeks
5 | 4. Stock/Inventory Operations | Reorder Level & Auto Replenishment | 1-Critical Core | HIGH | 3-4 weeks
6 | 4. Stock/Inventory Operations | Min-Max Stock Settings | 1-Critical Core | HIGH | 1-2 weeks
7 | 10. Utilities & Settings | Financial Year/Period Settings | 1-Critical Core | MEDIUM | 2-3 weeks
8 | 20. Authentication & Security | Two-Factor Authentication (2FA) | 1-Critical Core | HIGH | 3-4 weeks
9 | 16. CRM - Integration | Email Integration | 1-Critical Core | HIGH | 4-5 weeks
10 | 21. Audit & Compliance | Detailed Change Tracking | 1-Critical Core | MEDIUM | 3-4 weeks
11 | 16. CRM - Integration | Document Management | 1-Critical Core | MEDIUM | 4-5 weeks
12 | 7. Quality Control | Incoming Inspection (QC on GRN) | 2-Process Enhancement | MEDIUM | 3-4 weeks
13 | 7. Quality Control | Rejected/Quarantine Stock | 2-Process Enhancement | MEDIUM | 2-3 weeks
14 | 7. Quality Control | QC Certificate Management | 2-Process Enhancement | LOW | 2-3 weeks
15 | 2. Purchase Management | Request for Quotation (RFQ) | 2-Process Enhancement | MEDIUM | 3-4 weeks
16 | 2. Purchase Management | Vendor Bill/Invoice Matching | 2-Process Enhancement | MEDIUM | 4-5 weeks
17 | 9. Reports & Analytics | ABC Analysis | 2-Process Enhancement | MEDIUM | 2-3 weeks
18 | 9. Reports & Analytics | Slow-Moving/Non-Moving Stock Report | 2-Process Enhancement | MEDIUM | 2-3 weeks
19 | 9. Reports & Analytics | Reorder Report | 2-Process Enhancement | HIGH | 1-2 weeks
20 | 9. Reports & Analytics | Vendor Performance Report | 2-Process Enhancement | MEDIUM | 2-3 weeks
21 | 9. Reports & Analytics | Stock Aging Report | 2-Process Enhancement | MEDIUM | 2-3 weeks
22 | 9. Reports & Analytics | GRN vs PO Reconciliation | 2-Process Enhancement | MEDIUM | 2-3 weeks
23 | 15. CRM - Reports & Analytics | Conversion Rate Analytics | 2-Process Enhancement | MEDIUM | 2-3 weeks
24 | 15. CRM - Reports & Analytics | Sales Forecasting | 2-Process Enhancement | MEDIUM | 3-4 weeks
25 | 15. CRM - Reports & Analytics | Lead Source Effectiveness | 2-Process Enhancement | LOW | 2 weeks
26 | 15. CRM - Reports & Analytics | Custom Report Builder | 2-Process Enhancement | LOW | 4-5 weeks
27 | 13. CRM - Master Data | Payment Terms Master | 2-Process Enhancement | MEDIUM | 1 week
28 | 13. CRM - Master Data | Case Types/Categories | 2-Process Enhancement | LOW | 1 week
29 | 1. Master Data Management | HSN/SAC Code Master | 2-Process Enhancement | MEDIUM | 2-3 weeks
30 | 1. Master Data Management | Price List Master | 2-Process Enhancement | MEDIUM | 3-4 weeks
31 | 14. CRM - Workflows | Visual Workflow Builder | 2-Process Enhancement | MEDIUM | 4-5 weeks
32 | 14. CRM - Workflows | Automated Email Notifications | 2-Process Enhancement | MEDIUM | 3-4 weeks
33 | 14. CRM - Workflows | SLA Management | 2-Process Enhancement | LOW | 2-3 weeks
34 | 4. Stock/Inventory Operations | Expiry Date Management | 2-Process Enhancement | MEDIUM | 2-3 weeks
35 | 5. Warehouse Management (WMS) | Putaway Management | 3-Advanced Features | LOW | 3-4 weeks
36 | 5. Warehouse Management (WMS) | Picking List Generation | 3-Advanced Features | LOW | 3-4 weeks
37 | 5. Warehouse Management (WMS) | Cycle Count | 3-Advanced Features | LOW | 3-4 weeks
38 | 5. Warehouse Management (WMS) | Physical Stock Verification | 3-Advanced Features | LOW | 3-4 weeks
39 | 8. Production/Manufacturing | By-product/Scrap Entry | 3-Advanced Features | LOW | 2-3 weeks
40 | 19. Permission Management | Field-Level Permissions | 3-Advanced Features | HIGH | 3-4 weeks
41 | 19. Permission Management | Record-Level Permissions | 3-Advanced Features | HIGH | 3-4 weeks
42 | 19. Permission Management | Time-Based Permissions | 3-Advanced Features | LOW | 2-3 weeks
43 | 19. Permission Management | Permission Delegation | 3-Advanced Features | LOW | 2 weeks
44 | 17. User Management | User Impersonation | 3-Advanced Features | MEDIUM | 1-2 weeks
45 | 17. User Management | User Activity Tracking | 3-Advanced Features | LOW | 2-3 weeks
46 | 18. Role Management | Role Cloning/Duplication | 3-Advanced Features | LOW | 1 week
47 | 18. Role Management | Role Hierarchy | 3-Advanced Features | LOW | 2-3 weeks
48 | 18. Role Management | Role Templates | 3-Advanced Features | LOW | 2 weeks
49 | 20. Authentication & Security | OAuth Integration | 3-Advanced Features | MEDIUM | 2-3 weeks
50 | 20. Authentication & Security | SSO/SAML Integration | 3-Advanced Features | MEDIUM | 3-4 weeks
51 | 20. Authentication & Security | LDAP/AD Integration | 3-Advanced Features | MEDIUM | 3-4 weeks
52 | 20. Authentication & Security | Password Strength Enforcement | 3-Advanced Features | MEDIUM | 1 week
53 | 20. Authentication & Security | Password History | 3-Advanced Features | LOW | 1 week
54 | 21. Audit & Compliance | Audit Log Search & Filter | 3-Advanced Features | MEDIUM | 2-3 weeks
55 | 21. Audit & Compliance | GDPR Compliance Tools | 3-Advanced Features | MEDIUM | 3-4 weeks
56 | 21. Audit & Compliance | Data Retention Policies | 3-Advanced Features | LOW | 2 weeks
57 | 10. Utilities & Settings | Multi-Currency Settings | 3-Advanced Features | MEDIUM | 3-4 weeks
58 | 2. Purchase Management | Blanket/Contract Orders | 4-Integration | LOW | 3-4 weeks
59 | 5. Warehouse Management (WMS) | Cross-Docking | 4-Integration | LOW | 3-4 weeks
60 | 11. Integration Modules | E-commerce/Marketplace Sync | 4-Integration | LOW | 4-5 weeks
61 | 11. Integration Modules | Logistics/Shipping Integration | 4-Integration | LOW | 4-5 weeks
62 | 11. Integration Modules | Barcode Scanner/RFID Integration | 4-Integration | LOW | 2-3 weeks
63 | 19. Marketing Automation | Campaign Management | 4-Integration | LOW | 4-5 weeks
64 | 20. Workflow Automation | Visual Workflow Builder | 4-Integration | LOW | 5-6 weeks
65 | 21. Field-Level Security | Permission Matrix UI | 4-Integration | LOW | 2-3 weeks
66 | 22. User Experience | Dashboard Customization | 4-Integration | LOW | 3-4 weeks
67 | 22. User Experience | Saved Views/Filters | 4-Integration | LOW | 2-3 weeks
68 | 22. User Experience | Keyboard Shortcuts | 4-Integration | LOW | 1 week
69 | 22. User Experience | User Preferences | 4-Integration | LOW | 2-3 weeks
70 | 22. Notifications | Email Notifications | 4-Integration | MEDIUM | 2-3 weeks
71 | 22. Notifications | SMS Notifications | 4-Integration | LOW | 2-3 weeks
72 | 22. Notifications | Push Notifications | 4-Integration | LOW | 2-3 weeks
73 | 22. Notifications | Real-Time Notifications | 4-Integration | MEDIUM | 2-3 weeks
74 | 23. Multi-Currency Support | Exchange Rate Management | 4-Integration | LOW | 2-3 weeks
75 | 23. Multi-Currency Support | Currency Conversion Logic | 4-Integration | LOW | 3-4 weeks
76 | 23. Multi-Currency Support | Gain/Loss Calculation | 4-Integration | LOW | 2-3 weeks
77 | 24. Chart of Accounts | Account Hierarchy | 4-Integration | LOW | 2-3 weeks
78 | 24. Chart of Accounts | Journal Entry System | 4-Integration | LOW | 4-5 weeks
79 | 24. Chart of Accounts | Trial Balance | 4-Integration | LOW | 2-3 weeks
80 | 25. Calendar Integration | Google Calendar Sync | 4-Integration | LOW | 2-3 weeks
81 | 25. Calendar Integration | Outlook Calendar Sync | 4-Integration | LOW | 2-3 weeks
82 | 26. SMS & Push Notifications | SMS Gateway Setup | 4-Integration | LOW | 2 weeks
83 | 26. SMS & Push Notifications | Notification Templates | 4-Integration | LOW | 1 week
84 | 27. Social Media Integration | LinkedIn API | 4-Integration | LOW | 2-3 weeks
85 | 27. Social Media Integration | Twitter/X API | 4-Integration | LOW | 2-3 weeks
86 | 27. Social Media Integration | Facebook API | 4-Integration | LOW | 2-3 weeks
87 | 28. Customer Portal | Customer Authentication | 4-Integration | LOW | 2-3 weeks
88 | 28. Customer Portal | Self-Service Features | 4-Integration | LOW | 3-4 weeks
89 | 28. Customer Portal | Order Tracking | 4-Integration | LOW | 2-3 weeks
90 | 29. E-commerce Integration | Shopify/WooCommerce API | 4-Integration | LOW | 3-4 weeks
91 | 30. Shipping Integration | Shipping APIs (FedEx/UPS/DHL) | 4-Integration | LOW | 3-4 weeks

## Implementation Plan
RECOMMENDED IMPLEMENTATION PLAN
Phase | Module | Feature | Action Required | Est. Time | Dev Count
PHASE 1 (Months 1-2): Complete Partial Work | Multiple | All 20 Partial Features | Complete implementation of all partial features | 8-10 weeks | 3 developers
PHASE 1 (Months 3-4): Critical Core Features | 6. Stock Valuation | Full Costing Module | Implement tables, models, calculations, reports | 4 weeks | 2 developers
PHASE 1 (Months 3-4): Critical Core Features | 4. Stock/Inventory | Reorder Management | Reorder tables, auto-replenishment, alerts | 3 weeks | 1 developer
PHASE 1 (Months 3-4): Critical Core Features | 20. Authentication | 2FA Implementation | TOTP, backup codes, login flow update | 3 weeks | 1 developer
PHASE 1 (Months 3-4): Critical Core Features | 10. Utilities | Financial Year Settings | Financial years, periods, closing logic | 2 weeks | 1 developer
PHASE 1 (Months 3-4): Critical Core Features | 16. CRM Integration | Email Integration | Email service, templates, tracking, sync | 4 weeks | 1 developer
PHASE 2 (Months 5-6): Process Enhancement | 7. Quality Control | Full QC Module | QC workflow, inspection, certificates | 5 weeks | 1 developer
PHASE 2 (Months 5-6): Process Enhancement | 2. Purchase Management | RFQ & 3-Way Match | RFQ workflow, vendor matching, variance detection | 6 weeks | 2 developers
PHASE 2 (Months 6-7): Process Enhancement | 9. Reports & Analytics | Advanced Reports | Aging, ABC, slow-moving, vendor performance | 4 weeks | 1 developer
PHASE 2 (Months 7-8): Process Enhancement | 13. Master Data | Price List & HSN/SAC | Price lists, customer/supplier pricing, HSN/SAC master | 4 weeks | 1 developer
PHASE 2 (Months 7-8): Process Enhancement | 14. CRM Workflows | Advanced Workflows | Visual workflow builder, automation rules | 5 weeks | 1 developer
PHASE 3 (Months 9-10): Advanced Features | 5. WMS | Putaway & Picking | Putaway rules, picking lists, wave picking | 6 weeks | 1 developer
PHASE 3 (Months 10-11): Advanced Features | 19. Permissions | Advanced Security | Field-level, record-level, dynamic permissions | 6 weeks | 1 developer
PHASE 3 (Months 11-12): Advanced Features | 17. User/Role Mgmt | User Experience | Role hierarchy, impersonation, activity tracking | 4 weeks | 1 developer
PHASE 3 (Months 11-12): Advanced Features | 20. Authentication | Enterprise Auth | OAuth, SSO/SAML, LDAP, password policies | 5 weeks | 1 developer
PHASE 4 (Months 13-14): Integration | 11. Integration | E-commerce & Shipping | Shopify, WooCommerce, FedEx/UPS/DHL | 6 weeks | 1 developer
PHASE 4 (Months 14-15): Integration | 28. Customer Portal | Self-Service Portal | Customer auth, order tracking, invoices | 6 weeks | 1 developer
PHASE 4 (Months 15-16): Integration | 24. Accounting | Chart of Accounts | COA, journal entries, trial balance | 6 weeks | 2 developers

## Summary
PROJECT SUMMARY & STATISTICS
OVERALL PROJECT STATUS
Total Features | 174
Completed | 82 | 47.1%
Partial (Need Completion) | 20 | 11.5%
Not Started | 72 | 41.4%
Overall Completion (Weighted) | 52.9%
BY CATEGORY
Done (Ready for Use) | 82
Partial -> Complete | 20 | Need finishing
Pending (Not Started) | 72
BY PRIORITY
HIGH Priority Pending | ~25 features | Do first
MEDIUM Priority Pending | ~32 features | Do second
LOW Priority Pending | ~15 features | Do last
BY PHASE
Phase 1 (Months 1-4) | Critical Core | HIGH priority
Phase 2 (Months 5-8) | Process Enhancement | MEDIUM priority
Phase 3 (Months 9-12) | Advanced Features | LOW priority
Phase 4 (Months 13-16) | Integration & Extensions | LOW priority
TEAM REQUIREMENTS
Recommended Team Size | 3-5 developers + 1 QA + 1 UI/UX
Estimated Timeline | 12-16 months
IMMEDIATE ACTIONS (First 2 Weeks)
1. Complete Partial Features | 20 features | Highest ROI
2. Start Stock Valuation | High priority | Business critical
3. Start Reorder Management | High priority | Business critical
4. Implement 2FA | Security requirement